## UAT Report
				-- COPY THIS AREA IN THE ACK EMAIL BODY --
Big Project Cicle App

- Project Information -		- Test Result -				- Execution Plan -		- Actual Execution -
Report Date.	23 Oktober 2021	Status.				Start Date.	8-Oct-2021	Start Date.	8-Oct-2021
Project No.		Completion.				Finish Date.	23/10/2021	Finish Date.	23/10/2021
Test Cycle.		Total Test Case.	105
Test Env.	Staging
				Report Testing Cicle App - Manual
- Total Results To Date -
Status.	Planned #.	Planned %	Actual #.	Actual % from Result to Date.
Plan.	105	100.00%
			101	96.19%
			4	3.81%
			0	0.00%
			0	0.00%
			0	0.00%
			0	0.00%

- Defect / Issue Details -
Defect ID (#)	Defect Name	Priority		PIC	Status	Detected Date	Closed Date	Type
Bug001	Loading Notifications never Stop	Normal		Tim Development	Open	25-Oct-2021		ISSUE
Bug002	User Edit Due Date but less than today	Normal		Tim Development	Open	25-Oct-2021		ISSUE
Bug003	User attach the videos Group Chat	High		Tim Development	Open	25-Oct-2021		ISSUE
Bug004	User publish blast but Due date less than today	High		Tim Development	Open	25-Oct-2021		ISSUE
Bug005	User publish blast but Title is space	Normal		Tim Development	Open	25-Oct-2021		ISSUE
Bug006	User comment blast when blast is complete	Normal		Tim Development	Open	25-Oct-2021		ISSUE

No.	Type.	Scenario ID	Scenario Case					Result.	Blocked by (Defect ID)
1	Positve	Notif001	User Check Notifications	User Check Notifications	User Check Notifications	User Check Notifications	User Check Notifications	Tested Correctly
2	Positive	Notif002	User click mark all read Notifications	User click mark all read Notifications	User click mark all read Notifications	User click mark all read Notifications	User click mark all read Notifications	Tested Correctly
3	Positive	Notif003	User view all Notifications	User view all Notifications	User view all Notifications	User view all Notifications	User view all Notifications	Tested Correctly
4	Positive	Notif004	User check Cheers Notifications	User check Cheers Notifications	User check Cheers Notifications	User check Cheers Notifications	User check Cheers Notifications	Tested Correctly
5	Positive	Board01	User Add Card Name	User Add Card Name	User Add Card Name	User Add Card Name	User Add Card Name	Tested Correctly
6	Positive	Board02	User Add Card with minimal 1 Char	User Add Card with minimal 1 Char	User Add Card with minimal 1 Char	User Add Card with minimal 1 Char	User Add Card with minimal 1 Char	Tested Correctly
7	Positive	Board03	User Add Card with numeric	User Add Card with numeric	User Add Card with numeric	User Add Card with numeric	User Add Card with numeric	Tested Correctly
8	Positive	Board04	User Add Card with special Char	User Add Card with special Char	User Add Card with special Char	User Add Card with special Char	User Add Card with special Char	Tested Correctly			-- COPY THIS AREA IN THE ACK EMAIL BODY --
9	Negative	Board05	User Add Card but Card Name empty	User Add Card but Card Name empty	User Add Card but Card Name empty	User Add Card but Card Name empty	User Add Card but Card Name empty	Tested Correctly
10	Positive	Board06	User Add Card but Enabling Private Card	User Add Card but Enabling Private Card	User Add Card but Enabling Private Card	User Add Card but Enabling Private Card	User Add Card but Enabling Private Card	Tested Correctly
11	Positive	Board07	User move card	User move card	User move card	User move card	User move card	Tested Correctly
12	Positive	Board08	User Quick Comment	User Quick Comment	User Quick Comment	User Quick Comment	User Quick Comment	Tested Correctly
13	Positive	Board09	User set the Members	User set the Members	User set the Members	User set the Members	User set the Members	Tested Correctly
14	Positive	Board10	User Edit Labels	User Edit Labels	User Edit Labels	User Edit Labels	User Edit Labels	Tested Correctly
15	Positive	Board11	User Edit Due Date	User Edit Due Date	User Edit Due Date	User Edit Due Date	User Edit Due Date	Tested Correctly
16	Negative	Board12	User Edit Due Date but less than today	User Edit Due Date but less than today	User Edit Due Date but less than today	User Edit Due Date but less than today	User Edit Due Date but less than today	Tested with non Stopping Defect
17	Positive	Board13	User Edit Notes	User Edit Notes	User Edit Notes	User Edit Notes	User Edit Notes	Tested Correctly
18	Positive	Board14	User Change Name	User Change Name	User Change Name	User Change Name	User Change Name	Tested Correctly
19	Positive	Board15	User Attach Files	User Attach Files	User Attach Files	User Attach Files	User Attach Files	Tested Correctly
20	Positive	Board16	User set Public/Private Card	User set Public/Private Card	User set Public/Private Card	User set Public/Private Card	User set Public/Private Card	Tested Correctly
21	Positive	Board17	User archive card	User archive card	User archive card	User archive card	User archive card	Tested Correctly
22	Positive	Board18	User archive all cards in this list	User archive all cards in this list	User archive all cards in this list	User archive all cards in this list	User archive all cards in this list	Tested Correctly
23	Positive	Board19	User archive this list	User archive this list	User archive this list	User archive this list	User archive this list	Tested Correctly
24	Positive	Board20	User set as a complete list	User set as a complete list	User set as a complete list	User set as a complete list	User set as a complete list	Tested Correctly
25	Positive	Board21	user sort this list from A to Z	user sort this list from A to Z	user sort this list from A to Z	user sort this list from A to Z	user sort this list from A to Z	Tested Correctly
26	Positive	Board22	user sort this list from Z to A	user sort this list from Z to A	user sort this list from Z to A	user sort this list from Z to A	user sort this list from Z to A	Tested Correctly
27	Positive	Board23	User sort this list by Nearest Due Date	User sort this list by Nearest Due Date	User sort this list by Nearest Due Date	User sort this list by Nearest Due Date	User sort this list by Nearest Due Date	Tested Correctly
28	Positive	Board24	User sort this list by Furthest Due Date	User sort this list by Furthest Due Date	User sort this list by Furthest Due Date	User sort this list by Furthest Due Date	User sort this list by Furthest Due Date	Tested Correctly
29	Positive	Board25	User sort this list by Nearest Created Date	User sort this list by Nearest Created Date	User sort this list by Nearest Created Date	User sort this list by Nearest Created Date	User sort this list by Nearest Created Date	Tested Correctly
30	Positive	Board26	User sort this list by Furthest Created Date	User sort this list by Furthest Created Date	User sort this list by Furthest Created Date	User sort this list by Furthest Created Date	User sort this list by Furthest Created Date	Tested Correctly
31	Positive	Board27	User search cards based on Label Colour	User search cards based on Label Colour	User search cards based on Label Colour	User search cards based on Label Colour	User search cards based on Label Colour	Tested Correctly
32	Positive	Board28	User search cards based on member	User search cards based on member	User search cards based on member	User search cards based on member	User search cards based on member	Tested Correctly
33	Positive	Board29	User search based on Due Soon	User search based on Due Soon	User search based on Due Soon	User search based on Due Soon	User search based on Due Soon	Tested Correctly
34	Positive	Board30	User search based on Due Today	User search based on Due Today	User search based on Due Today	User search based on Due Today	User search based on Due Today	Tested Correctly
35	Positive	Board31	User search based on Overdue	User search based on Overdue	User search based on Overdue	User search based on Overdue	User search based on Overdue	Tested Correctly
36	Positive	Board32	User unarchive Card	User unarchive Card	User unarchive Card	User unarchive Card	User unarchive Card	Tested Correctly
37	Positive	Board33	User unarchive list card	User unarchive list card	User unarchive list card	User unarchive list card	User unarchive list card	Tested Correctly
38	Positive	Board34	User comment the card	User comment the card	User comment the card	User comment the card	User comment the card	Tested Correctly
39	Positive	Board35	User Delete comment the card	User Delete comment the card	User Delete comment the card	User Delete comment the card	User Delete comment the card	Tested Correctly
40	Positive	Board36	User Edit Comment the card	User Edit Comment the card	User Edit Comment the card	User Edit Comment the card	User Edit Comment the card	Tested Correctly
41	Positive	Board37	User give Cheers	User give Cheers	User give Cheers	User give Cheers	User give Cheers	Tested Correctly
42	Negative	Board38	User give Cheers Empty	User give Cheers Empty	User give Cheers Empty	User give Cheers Empty	User give Cheers Empty	Tested Correctly
43	Positive	Board39	User Reply this comment	User Reply this comment	User Reply this comment	User Reply this comment	User Reply this comment	Tested Correctly
44	Positive	Board40	User Add to members from comment	User Add to members from comment	User Add to members from comment	User Add to members from comment	User Add to members from comment	Tested Correctly
45	Positive	Board41	User Add the labels from comment	User Add the labels from comment	User Add the labels from comment	User Add the labels from comment	User Add the labels from comment	Tested Correctly
46	Positive	Board42	User Edit the due date from comment	User Edit the due date from comment	User Edit the due date from comment	User Edit the due date from comment	User Edit the due date from comment	Tested Correctly
47	Positive	Board43	User Attach Files from comment	User Attach Files from comment	User Attach Files from comment	User Attach Files from comment	User Attach Files from comment	Tested Correctly
48	Positive	Board44	User Move Card from comment	User Move Card from comment	User Move Card from comment	User Move Card from comment	User Move Card from comment	Tested Correctly
49	Positive	Board45	User set Public Card from comment	User set Public Card from comment	User set Public Card from comment	User set Public Card from comment	User set Public Card from comment	Tested Correctly
50	Positive	Board46	User Archive Card from comment	User Archive Card from comment	User Archive Card from comment	User Archive Card from comment	User Archive Card from comment	Tested Correctly
51	Positive	Board47	User Edit Notes from comment	User Edit Notes from comment	User Edit Notes from comment	User Edit Notes from comment	User Edit Notes from comment	Tested Correctly
52	Positive	Board48	User Edit Comment with format Bold	User Edit Comment with format Bold	User Edit Comment with format Bold	User Edit Comment with format Bold	User Edit Comment with format Bold	Tested Correctly
53	Positive	Board49	User Edit Comment with format Italic	User Edit Comment with format Italic	User Edit Comment with format Italic	User Edit Comment with format Italic	User Edit Comment with format Italic	Tested Correctly
54	Positive	Board50	User Edit Comment with format Strikethrough	User Edit Comment with format Strikethrough	User Edit Comment with format Strikethrough	User Edit Comment with format Strikethrough	User Edit Comment with format Strikethrough	Tested Correctly
55	Positive	Board51	User Edit Comment with format Background Colour	User Edit Comment with format Background Colour	User Edit Comment with format Background Colour	User Edit Comment with format Background Colour	User Edit Comment with format Background Colour	Tested Correctly
56	Positive	Board52	User Edit Comment with format Font Size	User Edit Comment with format Font Size	User Edit Comment with format Font Size	User Edit Comment with format Font Size	User Edit Comment with format Font Size	Tested Correctly
57	Positive	Board53	User Edit Comment with format More text	User Edit Comment with format More text	User Edit Comment with format More text	User Edit Comment with format More text	User Edit Comment with format More text	Tested Correctly
58	Positive	Board54	User Edit Comment with format Ordered List	User Edit Comment with format Ordered List	User Edit Comment with format Ordered List	User Edit Comment with format Ordered List	User Edit Comment with format Ordered List	Tested Correctly
59	Positive	Board55	User Edit Comment with format unordered List	User Edit Comment with format unordered List	User Edit Comment with format unordered List	User Edit Comment with format unordered List	User Edit Comment with format unordered List	Tested Correctly
60	Positive	Board56	User Edit Comment with format unordered More Paragraph	User Edit Comment with format unordered More Paragraph	User Edit Comment with format unordered More Paragraph	User Edit Comment with format unordered More Paragraph	User Edit Comment with format unordered More Paragraph	Tested Correctly
61	Positive	Board57	User Edit Comment with format Emoticon	User Edit Comment with format Emoticon	User Edit Comment with format Emoticon	User Edit Comment with format Emoticon	User Edit Comment with format Emoticon	Tested Correctly
62	Positive	Board58	User Edit Comment with format Files	User Edit Comment with format Files	User Edit Comment with format Files	User Edit Comment with format Files	User Edit Comment with format Files	Tested Correctly
63	Positive	Board59	User Edit Comment with format Insert Links	User Edit Comment with format Insert Links	User Edit Comment with format Insert Links	User Edit Comment with format Insert Links	User Edit Comment with format Insert Links	Tested Correctly
64	Positive	Board60	User Edit Comment with format More Rich	User Edit Comment with format More Rich	User Edit Comment with format More Rich	User Edit Comment with format More Rich	User Edit Comment with format More Rich	Tested Correctly
65	Positive	GroupChat01	User send Message is String Group Chat					Tested Correctly
66	Positive	GroupChat02	User send Message is Numeric Group Chat					Tested Correctly
67	Positive	GroupChat03	User send Message is Numeric Group Chat					Tested Correctly
68	Positive	GroupChat04	User send Message is GSM 7 Character Group Chat					Tested Correctly
69	Positive	GroupChat05	User send Message is UTF 8 Character Group Chat					Tested Correctly
70	Positive	GroupChat06	User send Message is Unicode Character Group Chat					Tested Correctly
71	Positive	GroupChat07	User send File Screenshots Group Chat					Tested Correctly
72	Negative	GroupChat08	User send File CSV Screenshots Group Chat					Tested Correctly
73	Negative	GroupChat09	User send File APK Group Chat					Tested Correctly
74	Positive	GroupChat10	User send File XLS Group Chat					Tested Correctly
75	Positive	GroupChat11	User send File Doc Screenshots Group Chat					Tested Correctly
76	Positive	GroupChat12	User send File PDF Screenshots Group Chat					Tested Correctly
77	Positive	GroupChat13	User send URL Group Chat					Tested Correctly
78	Positive	GroupChat14	User send messages 5000 char Group Chat					Tested Correctly
79	Positive	GroupChat15	User attach the videos Group Chat					Tested Correctly
80	Positive	GroupChat16	User attach the videos Maximum File Size Group Chat					Tested Correctly
81	Negative	GroupChat17	User send messages empty Group Chat					Tested Correctly
82	Positive	GroupChat18	User delete the chat					Tested Correctly
83	Positive	GroupChat19	User change Photo Profile from Group Chat					Tested Correctly
84	Positive	GroupChat20	User change Name Profile					Tested Correctly
85	Positive	Blast01	User publish blast					Tested Correctly
86	Positive	Blast02	User publish blast with title emoticon					Tested Correctly
87	Negative	Blast03	User publish blast but Due date less than today					Tested with non Stopping Defect
88	Negative	Blast04	User publish blast but Title is space					Tested with non Stopping Defect
89	Positive	Blast05	User comment blast when blast is complete					Tested with non Stopping Defect
90	Negative	Blast06	User publish blast but all mandatory empty					Tested Correctly
91	Positive	Blast07	User publish with set Notified					Tested Correctly
92	Positive	Blast08	User Blast message with format Bold					Tested Correctly
93	Positive	Blast09	User Blast message with format Italic					Tested Correctly
94	Positive	Blast10	User Blast message with format Strikethrough					Tested Correctly
95	Positive	Blast11	User Blast message with format Background Colour					Tested Correctly
96	Positive	Blast12	User Blast message with format Font Size					Tested Correctly
97	Positive	Blast13	User Blast message with format More text					Tested Correctly
98	Positive	Blast14	User Blast message with format Ordered List					Tested Correctly
99	Positive	Blast15	User Blast message with format unordered List					Tested Correctly
100	Positive	Blast16	User Blast message with format unordered More Paragraph					Tested Correctly
101	Positive	Blast17	User Blast message with format Emoticon					Tested Correctly
102	Positive	Blast18	User Blast message with format Files					Tested Correctly
103	Positive	Blast19	User Blast message with format Insert Links					Tested Correctly
104	Positive	Blast20	User Blast message with format More Rich					Tested Correctly
105	Positive	Blast21	User Complete the Post					Tested Correctly

## UAT Scenario
No	Scenario ID	Scenario Cases	Feature	Involved System or Application	Scenario Type	Planned Date	Execution Date	Status	Tester	Notes
1	Notif001	User Check Notifications	Notifications	Cicle	Positve	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
2	Notif002	User click mark all read Notifications	Notifications	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
3	Notif003	User view all Notifications	Notifications	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
4	Notif004	User check Cheers Notifications	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
5	Board01	User Add Card Name	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
6	Board02	User Add Card with minimal 1 Char	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
7	Board03	User Add Card with numeric	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
8	Board04	User Add Card with special Char	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
9	Board05	User Add Card but Card Name empty	Board	Cicle	Negative	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
10	Board06	User Add Card but Enabling Private Card	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
11	Board07	User move card	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
12	Board08	User Quick Comment	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
13	Board09	User set the Members	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
14	Board10	User Edit Labels	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
15	Board11	User Edit Due Date	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
16	Board12	User Edit Due Date but less than today	Board	Cicle	Negative	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
17	Board13	User Edit Notes	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
18	Board14	User Change Name	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
19	Board15	User Attach Files	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
20	Board16	User set Public/Private Card	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
21	Board17	User archive card	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
22	Board18	User archive all cards in this list	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
23	Board19	User archive this list	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
24	Board20	User set as a complete list	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
25	Board21	user sort this list from A to Z	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
26	Board22	user sort this list from Z to A	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
27	Board23	User sort this list by Nearest Due Date	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
28	Board24	User sort this list by Furthest Due Date	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
29	Board25	User sort this list by Nearest Created Date	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
30	Board26	User sort this list by Furthest Created Date	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
31	Board27	User search cards based on Label Colour	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
32	Board28	User search cards based on member	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
33	Board29	User search based on Due Soon	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
34	Board30	User search based on Due Today	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
35	Board31	User search based on Overdue	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
36	Board32	User unarchive Card	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
37	Board33	User unarchive list card	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
38	Board34	User comment the card	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
39	Board35	User Delete comment the card	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
40	Board36	User Edit Comment the card	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
41	Board37	User give Cheers	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
42	Board38	User give Cheers Empty	Board	Cicle	Negative	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
43	Board39	User Reply this comment	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
44	Board40	User Add to members from comment	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
45	Board41	User Add the labels from comment	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
46	Board42	User Edit the due date from comment	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
47	Board43	User Attach Files from comment	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
48	Board44	User Move Card from comment	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
49	Board45	User set Public Card from comment	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
50	Board46	User Archive Card from comment	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
51	Board47	User Edit Notes from comment	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
52	Board48	User Edit Comment with format Bold	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
53	Board49	User Edit Comment with format Italic	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
54	Board50	User Edit Comment with format Strikethrough	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
55	Board51	User Edit Comment with format Background Colour	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
56	Board52	User Edit Comment with format Font Size	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
57	Board53	User Edit Comment with format More text	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
58	Board54	User Edit Comment with format Ordered List	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
59	Board55	User Edit Comment with format unordered List	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
60	Board56	User Edit Comment with format unordered More Paragraph	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
61	Board57	User Edit Comment with format Emoticon	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
62	Board58	User Edit Comment with format Files	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
63	Board59	User Edit Comment with format Insert Links	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
64	Board60	User Edit Comment with format More Rich	Board	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
65	GroupChat01	User send Message is String Group Chat	Group Chat	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
66	GroupChat02	User send Message is Numeric Group Chat	Group Chat	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
67	GroupChat03	User send Message is Numeric Group Chat	Group Chat	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
68	GroupChat04	User send Message is GSM 7 Character Group Chat	Group Chat	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
69	GroupChat05	User send Message is UTF 8 Character Group Chat	Group Chat	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
70	GroupChat06	User send Message is Unicode Character Group Chat	Group Chat	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
71	GroupChat07	User send File Screenshots Group Chat	Group Chat	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
72	GroupChat08	User send File CSV Screenshots Group Chat	Group Chat	Cicle	Negative	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
73	GroupChat09	User send File APK Group Chat	Group Chat	Cicle	Negative	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
74	GroupChat10	User send File XLS Group Chat	Group Chat	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
75	GroupChat11	User send File Doc Screenshots Group Chat	Group Chat	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
76	GroupChat12	User send File PDF Screenshots Group Chat	Group Chat	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
77	GroupChat13	User send URL Group Chat	Group Chat	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
78	GroupChat14	User send messages 5000 char Group Chat	Group Chat	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
79	GroupChat15	User attach the videos Group Chat	Group Chat	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
80	GroupChat16	User attach the videos Maximum File Size Group Chat	Group Chat	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
81	GroupChat17	User send messages empty Group Chat	Group Chat	Cicle	Negative	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
82	GroupChat18	User delete the chat	Group Chat	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
83	GroupChat19	User change Photo Profile from Group Chat	Group Chat	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
84	GroupChat20	User change Name Profile	Group Chat	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
85	Blast01	User publish blast	Blast01	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
86	Blast02	User publish blast with title emoticon	Blast02	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
87	Blast03	User publish blast but Due date less than today	Blast03	Cicle	Negative	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
88	Blast04	User publish blast but Title is space	Blast04	Cicle	Negative	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
89	Blast05	User comment blast when blast is complete	Blast05	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
90	Blast06	User publish blast but all mandatory empty	Blast06	Cicle	Negative	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
91	Blast07	User publish with set Notified	Blast07	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
92	Blast08	User Blast message with format Bold	Blast08	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
93	Blast09	User Blast message with format Italic	Blast09	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
94	Blast10	User Blast message with format Strikethrough	Blast10	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
95	Blast11	User Blast message with format Background Colour	Blast11	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
96	Blast12	User Blast message with format Font Size	Blast12	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
97	Blast13	User Blast message with format More text	Blast13	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
98	Blast14	User Blast message with format Ordered List	Blast14	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
99	Blast15	User Blast message with format unordered List	Blast15	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
100	Blast16	User Blast message with format unordered More Paragraph	Blast16	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
101	Blast17	User Blast message with format Emoticon	Blast17	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
102	Blast18	User Blast message with format Files	Blast18	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
103	Blast19	User Blast message with format Insert Links	Blast19	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
104	Blast20	User Blast message with format More Rich	Blast20	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty
105	Blast21	User Complete the Post	Blast21	Cicle	Positive	08-10-2021	23-10-2021	Tested Correctly	Arisa Hazriaty

## Cases - Notifications
				Cicle - Cases Notifications
Test Case ID	Feature	Precondition	Positive/Negative	Scenario Name	Test Case Objective	Test Step	Expected Behaviour	Actual Behaviour	Result	Automated	Bug-ID
Notif001	Check Notif	User open the Boards	Positive	User Check Notifications	User able to Check All Notifications	-Signin Google / -Click Icon Notifications	All Notifications Display / Reminder Notification will hide	All Notifications Display / Reminder Notification will hide	Passed	No
Notif002			Positive	User click mark all read Notifications	User able to click mark all read Notifications	-Signin Google / -Click Mark all read Notifications	Update mark read notification and activities successful	Update mark read notification and activities successful	Passed	No
Notif003			Positive	User view all Notifications	User able to view all Notifications	-Signin Google / -View All Notification	All Notifications Display	All Notifications Display	Passed	No
Notif004			Positive	User check Cheers Notifications	User able to check Cheers Notifications	-Signin Google / -Click Cheers	All Cheers Display	All Cheers Display	Passed	No

				Total Scenario	4
				Total Scenario Passed	4
				Total Scenario Failed	0
				Total Scenario Automated	0
				Total Scenario Running Manual	4
				Total Scenario Positive	4
				Total Scenario Negative	0

## Cases - Feature Board
Test Case ID	Feature	Precondition	Positive/Negative	Scenario Name	Test Case Objective	Test Step	Expected Behaviour	Actual Behaviour	Result	Automated	Bug-ID
Board01	Add Card	User open the Boards	Positive	User Add Card Name	User able to add Card	-Signin Google / -Click Group Soal A / -Click Board / -Select List Action / -Click Icon Add Card / -Set the card name / -Click Add Card Button	Creating card is success / Card display on board	Creating card is success / Card display on board	Passed	Yes
Board02			Positive	User Add Card with minimal 1 Char	User able to Add Card with minimal 1 Char	-Signin Google / -Click Group Soal A / -Click Board / -Select List Action / -Click Icon Add Card / -Set the card name / -Click Add Card Button	Creating card is success / Card display on board	Creating card is success / Card display on board	Passed	No
Board03			Positive	User Add Card with numeric	User able to Add Card with minimal 1 Char	-Signin Google / -Click Group Soal A / -Click Board / -Select List Action / -Click Icon Add Card / -Set the card 1 char / -Click Add Card Button	Creating card is success / Card display on board	Creating card is success / Card display on board	Passed	No
Board04			Positive	User Add Card with special Char	User able to Add Card with special Char	-Signin Google / -Click Group Soal A / -Click Board / -Select List Action / -Click Icon Add Card / -Set the card with special Char / -Click Add Card Button	Creating card is success / Card display on board	Creating card is success / Card display on board	Passed	No
Board05			Negative	User Add Card but Card Name empty	User able to add Card	-Signin Google / -Click Group Soal A / -Click Board / -Select List Action / -Click Icon Add Card / -Set the card name Empty / -Click Add Card Button	Card name cannot be empty	Card name cannot be empty	Passed	Yes
Board06			Positive	User Add Card but Enabling Private Card	User able to Add Card but Enabling Private Card	-Signin Google / -Click Group Soal A / -Click Board / -Select List Action / -Click Icon Add Card / -Set the card name / - Set Private Card is on / - Click Add Card Button	Creating card is success / Card display on board	Creating card is success / Card display on board	Passed	Yes
Board07	Move Card		Positive	User move card	User able to move card	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Select Move Card / -Select list board / -Click Move	Move card is success / Card is moved and display	Move card is success / Card is moved and display	Passed	Yes
Board08			Positive	User Quick Comment	User able to Add Quick Comment	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Select Quick Comment / -Add New Comment / -Input Comment / -Click Save	Create comment is success / Comment displayed on top	Create comment is success / Comment displayed on top	Passed	Yes
Board09			Positive	User set the Members	User set the Members	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Select Change Members / -Set Team Members / -Click icon close	Toogle member card is success	Toogle member card is success	Passed	No
Board10			Positive	User Edit Labels	User able to add Labels	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Select Edit Labels / -Create New Label / -Input Name / -Select Color / - Click Create Button	Creating label for this board is success / Label selected is displayed	Creating label for this board is success / Label selected is displayed	Passed	No
Board11			Positive	User Edit Due Date	User able to edit Due Date	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Select Edit Due Date / -Set the Date / -Set the Time / -Click Save Button	Update Card is success	Update Card is success	Passed	Yes
Board12			Negative	User Edit Due Date but less than today	User not able to Edit Due Date but less than today	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Select Edit Due Date / -Set the Date / -Set the Time / -Click Save Button	Due date cannot be less than today	Update Card is success	Failed	No
Board13			Positive	User Edit Notes	User able to edit Notes	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Select Edit Notes / -Input Notes / -Click Save Button	Update Card is success	Update Card is success	Passed	Yes
Board14			Positive	User Change Name	User able to change name card	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Select Change Name / -Edit Card Name / -Click Save Button	Update Card is success	Update Card is success	Passed	Yes
Board15			Positive	User Attach Files	User able to attach Files	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Select Attach Files / -Choose File	Upload attachment is success / File attachment is displayed	Upload attachment is success / File attachment is displayed	Passed	No
Board16			Positive	User set Public/Private Card	User able to set Public/Private Card	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Set Public/Private Card	Upload attachment is success / Icon Public/Private card is displayed	Upload attachment is success / Icon Public/Private card is displayed	Passed	No
Board17			Positive	User archive card	User able to archive card	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Select Archive	Archiving card is success / Card is hidden	Archiving card is success / Card is hidden	Passed	No
Board18	List Action		Positive	User archive all cards in this list	User able to archive all cards in this list	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Select Archive All cards in this list	Archive card is success / All Card is hidden	Archiving card is success / Card is hidden	Passed	No
Board19			Positive	User archive this list	User able to archive this list	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Select Archive this list	Archive list this card is success	Archive list this card is success	Passed	No
Board20			Positive	User set as a complete list	User able to set as a complete list	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Select Set as a Complete list	Set list as Complete is success	Set list as Complete is success	Passed	No
Board21			Positive	user sort this list from A to Z	User able to sort list from A to Z	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Select sort this list from A to Z	Sort this list from A to Z is success	Sort this list from A to Z is success	Passed	No
Board22			Positive	user sort this list from Z to A	User able to sort list from Z to A	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Select sort this list from A to Z	Sort this list from Z to A is success	Sort this list from Z to A is success	Passed	No
Board23			Positive	User sort this list by Nearest Due Date	User able to this list by Nearest Due Date	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Select Sort list by Nearest Due Date	Sort list by Nearest Due Date is success	Sort list by Nearest Due Date is success	Passed	No
Board24			Positive	User sort this list by Furthest Due Date	User able to sort this list by Furthest Due Date	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Select Sort list by Furthest Due Date	Sort list by Furthest Due Date is success	Sort list by Furthest Due Date is success	Passed	No
Board25			Positive	User sort this list by Nearest Created Date	User able to sort this list by Nearest Created Date	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Select Sort list by Nearest Created Date	Sort list by Nearest Created Date is success	Sort list by Nearest Created Date is success	Passed	No
Board26			Positive	User sort this list by Furthest Created Date	User able to sort this list by Furthest Created Date	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Select list by Furthest Created	Sort list by Furthest Created Date is success	Sort list by Furthest Created Date is success	Passed	No
Board27	Search Cards		Positive	User search cards based on Label Colour	User able to search cards based on Label Colour	-Signin Google / -Click Group Soal A / -Click Board / -Click Icon search / -Select the label	Search based on label color is displayed	Search based on label color is displayed	Passed	No
Board28			Positive	User search cards based on member	User able to search cards based on member	-Signin Google / -Click Group Soal A / -Click Board / -Click Icon search / -Select member	Search based on member is displayed	Search based on member is displayed	Passed	No
Board29			Positive	User search based on Due Soon	User able to search based on Due Soon	-Signin Google / -Click Group Soal A / -Click Board / -Click Icon search / -Select Due Soon	Search based on Due Soon is displayed	Search based on Due Soon is displayed	Passed	No
Board30			Positive	User search based on Due Today	User able to search based on Due Today	-Signin Google / -Click Group Soal A / -Click Board / -Click Icon search / -Select Due Today	Search based on Due Today is displayed	Search based on Due Today is displayed	Passed	No
Board31			Positive	User search based on Overdue	User able to search based on Overdue	-Signin Google / -Click Group Soal A / -Click Board / -Click Icon search / -Select Overdue	Search based on Overdue is displayed	Search based on Overdue is displayed	Passed	No
Board32	Unarchive Cards		Positive	User unarchive Card	User able to unarchive items	-Signin Google / -Click Group Soal A / -Click Board / -Click Icon Archived Items / -Search Cards / -Click Restore	Unarchiving card is success	Unarchiving card is success	Passed	No
Board33	Unarchive list cards		Positive	User unarchive list card	User able to unarchive list card	-Signin Google / -Click Group Soal A / -Click Board / -Click Icon Archived Items / -Click Switch to lists / -Select list card / -Click Restore	Unarchiving list with card is success	Unarchiving list with card is success	Passed	Yes
Board34	Comment Card		Positive	User comment the card	User able to comment the card	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Click icon Comment / -Put the comment / -Click Save Button	Create comment is success	Create comment is success	Passed	Yes
Board35			Positive	User Delete comment the card	User able to Delete comment the card	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Click icon Comment / -Select comment will be deleted / -Click Delete Button	Delete Comment is success	Delete Comment is success	Passed	No
Board36			Positive	User Edit Comment the card	User able to Edit Comment the card	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Click icon Comment / -Select comment will be edit / -Set the Comment / -Click Save Button	Update Comment is success	Update Comment is success	Passed	No
Board37			Positive	User give Cheers	User able to give Cheers	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Click icon Comment / -Click Icon Cheers / -Put the cheers / -Click Icon Checklist	Create cheers on card comment successfull	Create cheers on card comment successfull	Passed	No
Board38			Negative	User give Cheers Empty	User not able to give Cheers Empty	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Click icon Comment / -Click Icon Cheers / -Put the cheers empty / -Click Icon Checklist	Cheer cannot be empty	Cheer cannot be empty	Passed	No
Board39			Positive	User Reply this comment	User able to Reply this comment	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Click icon Comment / -Select Comment / -Put New Comment / -Click Icon Checklist	Create discussion on card moment successfull	Create discussion on card moment successfull	Passed	No
Board40			Positive	User Add to members from comment	User able to Add member from feature comment	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Click icon Comment / -Select icon Add Members / -Set the members	Toogle member card is success	Toogle member card is success	Passed	No
Board41			Positive	User Add the labels from comment	User able to Add the labels	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Click icon Comment / -Select icon labels / -Set The label/Create	Creating label for this board is success / Label selected is displayed	Creating label for this board is success / Label selected is displayed	Passed	No
Board42			Positive	User Edit the due date from comment	User able to Edit the due date	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Click icon Comment / -Select icon Due Date / -Set the date / -Click Save Button	Update Card is success	Update Card is success	Passed	No
Board43			Positive	User Attach Files from comment	User able to Attached Files from comment	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Click icon Comment / -Select Attach File / -Choose file / -Click Open	Upload attachment is success / File attachment is displayed	Upload attachment is success / File attachment is displayed	Passed	No
Board44			Positive	User Move Card from comment	User able to Move Card from comment	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Click icon move card / -Select the list / -Click Move Button	Move card is success / Card is moved and display	Move card is success / Card is moved and display	Passed	Yes
Board45			Positive	User set Public Card from comment	User able to set Public Card from comment	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Click icon Public/Private Card	Update Card is success / Icon Public/Private card is displayed	Update Card is success / Icon Public/Private card is displayed	Passed	No
Board46			Positive	User Archive Card from comment	User able to Archive Card from comment	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Click icon Archiving Card	Archiving card is success / Icon Archiving card is hidden	Archiving card is success / Icon Archiving card is hidden	Passed	No
Board47			Positive	User Edit Notes from comment	User able to Edit Notes from comment	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Click icon edit comment / -Click Save Button	Update Card is success / Notes display latest update	Update Card is success / Notes display latest update	Passed	No
Board48	Add/Edit Comment		Positive	User Edit Comment with format Bold	User able to Edit Comment with format Bold	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Set Comment with format Bold / -Click Save	Comment can be set based on specified criteria / Add/Edit Comment successfull	Comment can be set based on specified criteria / Add/Edit Comment successfull	Passed	No
Board49			Positive	User Edit Comment with format Italic	User able to Edit Comment with format Italic	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Set Comment with format Italic / -Click Save	Comment can be set based on specified criteria / Add/Edit Comment successfull	Comment can be set based on specified criteria / Add/Edit Comment successfull	Passed	No
Board50			Positive	User Edit Comment with format Strikethrough	User able to Edit Comment with format Strikethrough	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Set Comment with format Strikethrough / -Click Save	Comment can be set based on specified criteria / Add/Edit Comment successfull	Comment can be set based on specified criteria / Add/Edit Comment successfull	Passed	No
Board51			Positive	User Edit Comment with format Background Colour	User able to Edit Comment with format Background Colour	-Signin Google / -Click Group Soal A / -Choose Blast / -Put the title / -Set Message with format Background Color / -Click Publish	Comment can be set based on specified criteria / Add/Edit Comment successfull	Comment can be set based on specified criteria / Add/Edit Comment successfull	Passed	No
Board52			Positive	User Edit Comment with format Font Size	User able to Edit Comment with format Font Size	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Set Message with format Font Size / -Click Save	Comment can be set based on specified criteria / Add/Edit Comment successfull	Comment can be set based on specified criteria / Add/Edit Comment successfull	Passed	No
Board53			Positive	User Edit Comment with format More text	User able to Edit Comment with format More text	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Set Comment with format More Text / -Click Save	Comment can be set based on specified criteria / Add/Edit Comment successfull	Comment can be set based on specified criteria / Add/Edit Comment successfull	Passed	No
Board54			Positive	User Edit Comment with format Ordered List	User able to Edit Comment with format Ordered List	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Set Comment with format Ordered List / -Click Publish	Comment can be set based on specified criteria / Add/Edit Comment successfull	Comment can be set based on specified criteria / Add/Edit Comment successfull	Passed	No
Board55			Positive	User Edit Comment with format unordered List	User able to Edit Comment with format unordered List	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Set Comment with format unordered List / -Click Save	Comment can be set based on specified criteria / Add/Edit Comment successfull	Comment can be set based on specified criteria / Add/Edit Comment successfull	Passed	No
Board56			Positive	User Edit Comment with format unordered More Paragraph	User able to Edit Comment with format More Paragraph	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Set Comment with format More paragraph / -Click Save	Comment can be set based on specified criteria / Add/Edit Comment successfull	Comment can be set based on specified criteria / Add/Edit Comment successfull	Passed	No
Board57			Positive	User Edit Comment with format Emoticon	User able to Edit Comment with format Emoticon	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Set Comment with format Emoticon / -Click Save	Comment can be set based on specified criteria / Add/Edit Comment successfull	Comment can be set based on specified criteria / Add/Edit Comment successfull	Passed	No
Board58			Positive	User Edit Comment with format Files	User able to Edit Comment with format Files	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Set Message with format Files / -Click Save	Comment can be set based on specified criteria / Add/Edit Comment successfull	Comment can be set based on specified criteria / Add/Edit Comment successfull	Passed	No		Cicle - Scenario Feature Board
Board59			Positive	User Edit Comment with format Insert Links	User able to Edit Comment with format Insert Links	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Set Message with format Insert Links / -Click Save	Comment can be set based on specified criteria / Add/Edit Comment successfull	Comment can be set based on specified criteria / Add/Edit Comment successfull	Passed	No
Board60			Positive	User Edit Comment with format More Rich	User able to Edit Comment with format More Rich	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Set Message with format Imore Rich / -Click Save	Comment can be set based on specified criteria / Add/Edit Comment successfull	Comment can be set based on specified criteria / Add/Edit Comment successfull	Passed	No
									Total Scenario	60
									Total Scenario Passed	59
									Total Scenario Failed	1
									Total Scenario Automated	11
									Total Scenario Running Manual	49
									Total Scenario Positive	57
									Total Scenario Negative	3

## UAT Report
Two Wheelers EFP

- Project Information -		- Test Result -				- Execution Plan -		- Actual Execution -
Report Date.	23-Oct-21	Status.	OK			Start Date.	Dec 30, 99	Start Date.	Dec 30, 99
Project No.	UAT	Completion.	100% Tested Correctly / 100% Executed			Finish Date.	Dec 30, 99	Finish Date.	Dec 30, 99
Test Env.	C1	Total Test Case.	91
					Two Wheelers EFP
- Total Results To Date -
Status.	Planned #.	Planned %	Actual #.	Actual % from Result to Date.
Plan.	100	100%	100	100%
Tested correctly	100	100%	100	100%
Tested with non Stopping Defect			0	0%
Tested with Showstopper			0	0%
In Progress			0	0%
N/A			0	0%
Not Tested			0	0%

- Defect / Issue Details -
Defect ID (#)	Defect Name	Description		PIC	Status	Detected Date	Closed Date	Type	Blocked Test Case
Bug001	Loading Notifications never Stop	Normal		All Notifications displayed correctly	Open	25-Oct-2021	30-Dec-1899	0	0
#NAME?	#NAME?	#NAME?		#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?
#NAME?	#NAME?	#NAME?		#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?
#NAME?	#NAME?	#NAME?		#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?
#NAME?	#NAME?	#NAME?		#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?
#NAME?	#NAME?	#NAME?		#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?
#NAME?	#NAME?	#NAME?		#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?

No.	Type.	Scenario ID	Scenario Case					Result.
1	Err:509	Err:509	Err:509					Err:509
2	Err:509	Err:509	Err:509					Err:509
3	Err:509	Err:509	Err:509					Err:509
4	Err:509	Err:509	Err:509					Err:509
5	Positive	User Change Name	Err:509					Tested Correctly
6	Err:509	Err:509	Err:509					Err:509
7	Err:509	User Attach Files	Err:509					Err:509
8	Positive	Err:509	user sort this list from A to Z					Tested Correctly
9	#NAME?	User set Public/Private Card	Err:509					#NAME?
10	#NAME?	User archive card	Err:509					#NAME?
11	Err:509	Err:509	Err:509					Err:509
12	Err:509	Err:509	Err:509					Err:509
13	Err:509	Err:509	Err:509					Err:509
14	Err:509	Err:509	Err:509					Err:509

## SIT Scenario
No	Scenario ID	Scenario Cases	Product Code	Involved System or Application	Pre Condition	Scenario Type	Planned Date	Execution Date	Status	Tester	Notes

## Reff Table
Test Cycle	Test Env	Progress / Result	Test Priority	Scenario Type	Status	Defect / Issue	Defect Status
SIT	C1	OK	High	Positive	Tested correctly	DEFECT	Open
	PreProd	OK	High	Positive	Tested correctly	DEFECT	Open
UAT	C2	NOT OK	Medium	Negative	Tested with non Stopping Defect	ISSUE	In Progress
	C3	In Progress	Low	Regression	Not Tested		Closed
	PreProd		Critical		N/A
	Production				In Progress
					Tested with Showstopper

## Cases - Feature Group Chat
				Cicle - Case Feature Group Chat
Test Case ID	Feature	Precondition	Positive/Negative	Scenario Name	Test Case Objective	Test Step	Expected Behaviour	Actual Behaviour	Result	Automated	Bug-ID
GroupChat01	Send Message	User open the Group Chat	Positive	User send Message is String Group Chat	User able to send Message is String Group Chat	-Signin Google / -Click Group Soal A / -Click Group Chat / -Put the Message is Integer / -Click Icon yellow Chat Button	Success Send Message Group / Message is display latest	Success Send Message Group / Message is display latest	Passed	Yes
GroupChat02			Positive	User send Message is Numeric Group Chat	User able to send Message is Numeric Group Chat	-Signin Google / -Click Group Soal A / -Click Group Chat / -Put the Message is Numeric / -Click Icon yellow Chat Button	Success Send Message Group / Message is display latest	Success Send Message Group / Message is display latest	Passed	Yes
GroupChat03			Positive	User send Message is Numeric Group Chat	User able to send Message is Numeric Group Chat	-Signin Google / -Click Group Soal A / -Click Group Chat / -Put the Message is Numeric / -Click Icon yellow Chat Button	Success Send Message Group / Message is display latest	Success Send Message Group / Message is display latest	Passed	Yes
GroupChat04			Positive	User send Message is GSM 7 Character Group Chat	User able to send Message is GSM 7 Character Group Chat	-Signin Google / -Click Group Soal A / -Click Group Chat / -Put the Message is GSM 7 Chars / -Click Icon yellow Chat Button	Success Send Message Group / Message is display latest	Success Send Message Group / Message is display latest	Passed	Yes
GroupChat05			Positive	User send Message is UTF 8 Character Group Chat	User able to send Message is UTF 8 Character Group Chat	-Signin Google / -Click Group Soal A / -Click Group Chat / -Put the message is UTF 8 / -Click Icon yellow Chat Button	Success Send Message Group / Message is display latest	Success Send Message Group / Message is display latest	Passed	No
GroupChat06			Positive	User send Message is Unicode Character Group Chat	User send Message is GSM 7 Character Group Chat	-Signin Google / -Click Group Soal A / -Click Group Chat / -Put the Message is Unicode / -Click Icon yellow Chat Button	Success Send Message Group / Message is display latest	Success Send Message Group / Message is display latest	Passed	Yes
GroupChat07			Positive	User send File Screenshots Group Chat	User able to send File Group chat	-Signin Google / -Click Group Soal A / -Click Group Chat / -Click Icon attach file / -Choose File	Success Send Message Group / File is display latest	Success Send Message Group / File is display latest	Passed	Yes
GroupChat08			Negative	User send File CSV Screenshots Group Chat	User not able to send File CSV Screenshots Group Chat	-Signin Google / -Click Group Soal A / -Click Group Chat / -Click Icon attach file / -Choose File CSV	Format File Cannot be allowed	Format File Cannot be allowed	Passed	No
GroupChat09			Negative	User send File APK Group Chat	User not able to send File APK Group Chat	-Signin Google / -Click Group Soal A / -Click Group Chat / -Click Icon attach file / -Choose File APK	Format File Cannot be allowed	Format File Cannot be allowed	Passed	No
GroupChat10			Positive	User send File XLS Group Chat	User able to send File XLS Screenshots Group Chat	-Signin Google / -Click Group Soal A / -Click Group Chat / -Click Icon attach file / -Choose File XLS	Success Send Message Group / File is display latest	Success Send Message Group / File is display latest	Passed	Yes
GroupChat11			Positive	User send File Doc Screenshots Group Chat	User able to send File Doc Screenshots Group Chat	-Signin Google / -Click Group Soal A / -Click Group Chat / -Click Icon attach file / -Choose File Doc	Success Send Message Group / File is display latest	Success Send Message Group / File is display latest	Passed	Yes
GroupChat12			Positive	User send File PDF Screenshots Group Chat	User send File PDF Screenshots Group Chat	-Signin Google / -Click Group Soal A / -Click Group Chat / -Click Icon attach file / -Choose File Doc	Success Send Message Group / File is display latest	Success Send Message Group / File is display latest	Passed	No
GroupChat13			Positive	User send URL Group Chat	User able to send URL link Group Chat	-Signin Google / -Click Group Soal A / -Click Group Chat / -Click Icon attach file / -Choose File	Success Send Message Group / URL display latest	Success Send Message Group / URL display latest	Passed	Yes
GroupChat14			Positive	User send messages 5000 char Group Chat	User able to send messages 5000 char Group Chat	-Signin Google / -Click Group Soal A / -Click Group Chat / -Put message 5000 Chars / -Choose File Videos	Success Send Message Group / Messages is display latest	Success Send Message Group / Messages is display latest	Passed	Yes
GroupChat15			Positive	User attach the videos Group Chat	User able to attached videos the videos Group Chat	-Signin Google / -Click Group Soal A / -Click Group Chat / -Click Icon Attach / -Choose Video File	Success Send Message Group / Videos is display latest	Success Send Message Group / Videos display latest / Blank Video after Downloaded	Failed	Yes	Bug001
GroupChat16			Positive	User attach the videos Maximum File Size Group Chat	User not able attach the videos Maximum File Size Group Chat	-Signin Google / -Click Group Soal A / -Click Group Chat / -Click Icon Attach / -Choose Video File	User not able attach the videos Maximum File Size Group Chat	User not able attach the videos Maximum File Size Group Chat	Passed	No
GroupChat17			Negative	User send messages empty Group Chat	Send Message cannot be empty	-Signin Google / -Click Group Soal A / -Click Group Chat / -Click Icon yellow Chat Button	System does not respon when user send message is empty	System does not respon when user send message is empty	Passed	Yes
GroupChat18	Delete Chat		Positive	User delete the chat	User able to deleted the chat	-Signin Google / -Click Group Soal A / -Click Group Chat / -Select Chat will be deleted / -Click Delete Message	Delete Group Chat Mesaage success	Delete Group Chat Mesaage success	Passed	Yes
GroupChat19	Edit Profile		Positive	User change Photo Profile from Group Chat	User able change Photo Profile from Group Chat	-Signin Google / -Click Group Soal A / -Click Group Chat / -Click Photo Profile / -Change Photo Profile	Change Photo Profile is success	Change Photo Profile is success	Passed	No
GroupChat20			Positive	User change Name Profile	User able to changed Photo Profile from Group Chat	-Signin Google / -Click Group Soal A / -Click Group Chat / -Click Photo Profile / -Set name Profile / -Click Save	Update Name Profile is success	Update Name Profile is success	Passed	No
				Total Scenario	20
				Total Scenario Passed	19
				Total Scenario Failed	1
				Total Scenario Automated	13
				Total Scenario Running Manual	7
				Total Scenario Positive	17
				Total Scenario Negative	3

## Cases - Feature Blast
				Cicle - Case Feature Blast
Test Case ID	Feature	Precondition	Positive/Negative	Scenario Name	Test Case Objective	Test Step	Expected Behaviour	Actual Behaviour	Result	Automated	Bug-ID
Blast01		User open the Group Chat	Positive	User publish blast	User able to publish blast	-Signin Google / -Click Group Soal A / -Choose Blast / -Put the title / -Put the story / -set the Due Date / -Click Publish	Create Post successfull	Create Post successfull	Passed	Yes
Blast02			Positive	User publish blast with title emoticon	User able publish blast with title emoticon	-Signin Google / -Click Group Soal A / -Choose Blast / -Put the title / -Put the story / -set the Due Date / -Click Publish	Create Post successfull	Create Post successfull	Passed	Yes
Blast03			Negative	User publish blast but Due date less than today	User not able publish blast but Due date less than today	-Signin Google / -Click Group Soal A / -Choose Blast / -Put the title / -Put the story / -set the Due Date less than today / -Click Publish	User not able publish blast but Due date less than today	Create Post successfull	Failed	No
Blast04			Negative	User publish blast but Title is space	User not able publish blast but Title is space	-Signin Google / -Click Group Soal A / -Choose Blast / -Put the title space / -Click Publish	User not able publish blast but Title is space	Create Post successfull	Failed	No
Blast05			Positive	User comment blast when blast is complete	User able to comment blast when blast is complete	-Signin Google / -Click Group Soal A / -Choose Blast / -Select Blast with status complete / -Put the comment / -Click Save	User able to comment blast when blast is complete	Something When Wrong	Failed	No
Blast06			Negative	User publish blast but all mandatory empty	All mandatory field cannot be empty	-Signin Google / -Click Group Soal A / -Choose Blast / -Click Publish	Field Parameter not complete	Field Parameter not complete	Passed	Yes
Blast07			Positive	User publish with set Notified	User able to publish with set Notified	-Signin Google / -Click Group Soal A / -Choose Blast / -Put the title / -Put the story / -set the Due Date / - Set notified / -Click Publish	Create Post successfull	Create Post successfull	Passed	Yes
Blast08	Set Format Message		Positive	User Blast message with format Bold	User able to Blast message with format Bold	-Signin Google / -Click Group Soal A / -Choose Blast / -Put the title / -Set Message with format Bold / -Click Publish	Message can be set based on specified criteria / Create Post successfull	Message can be set based on specified criteria / Create Post successfull	Passed	No
Blast09			Positive	User Blast message with format Italic	User able to Blast message with format Italic	-Signin Google / -Click Group Soal A / -Choose Blast / -Put the title / -Set Message with format Italic / -Click Publish	Message can be set based on specified criteria / Create Post successfull	Message can be set based on specified criteria / Create Post successfull	Passed	No
Blast10			Positive	User Blast message with format Strikethrough	User able to Blast message with format Strikethrough	-Signin Google / -Click Group Soal A / -Choose Blast / -Put the title / -Set Message with format Strikethrough / -Click Publish	Message can be set based on specified criteria / Create Post successfull	Message can be set based on specified criteria / Create Post successfull	Passed	No
Blast11			Positive	User Blast message with format Background Colour	User able to Blast message with format Background Colour	-Signin Google / -Click Group Soal A / -Choose Blast / -Put the title / -Set Message with format Background Color / -Click Publish	Message can be set based on specified criteria / Create Post successfull	Message can be set based on specified criteria / Create Post successfull	Passed	No
Blast12			Positive	User Blast message with format Font Size	User able to Blast message with format Font Size	-Signin Google / -Click Group Soal A / -Choose Blast / -Put the title / -Set Message with format Font Size / -Click Publish	Message can be set based on specified criteria / Create Post successfull	Message can be set based on specified criteria / Create Post successfull	Passed	No
Blast13			Positive	User Blast message with format More text	User able to Blast message with format More text	-Signin Google / -Click Group Soal A / -Choose Blast / -Put the title / -Set Message with format More Text / -Click Publish	Message can be set based on specified criteria / Create Post successfull	Message can be set based on specified criteria / Create Post successfull	Passed	No
Blast14			Positive	User Blast message with format Ordered List	User able to Blast message with format Ordered List	-Signin Google / -Click Group Soal A / -Choose Blast / -Put the title / -Set Message with format Ordered List / -Click Publish	Message can be set based on specified criteria / Create Post successfull	Message can be set based on specified criteria / Create Post successfull	Passed	No
Blast15			Positive	User Blast message with format unordered List	User able to Blast message with format unordered List	-Signin Google / -Click Group Soal A / -Choose Blast / -Put the title / -Set Message with format unordered List / -Click Publish	Message can be set based on specified criteria / Create Post successfull	Message can be set based on specified criteria / Create Post successfull	Passed	No
Blast16			Positive	User Blast message with format unordered More Paragraph	User able to Blast message with format More Paragraph	-Signin Google / -Click Group Soal A / -Choose Blast / -Put the title / -Set Message with format More paragraph / -Click Publish	Message can be set based on specified criteria / Create Post successfull	Message can be set based on specified criteria / Create Post successfull	Passed	No
Blast17			Positive	User Blast message with format Emoticon	User able to Blast message with format Emoticon	-Signin Google / -Click Group Soal A / -Choose Blast / -Put the title / -Set Message with format Emoticon / -Click Publish	Message can be set based on specified criteria / Create Post successfull	Message can be set based on specified criteria / Create Post successfull	Passed	No
Blast18			Positive	User Blast message with format Files	User able to Blast message with format Files	-Signin Google / -Click Group Soal A / -Choose Blast / -Put the title / -Set Message with format Files / -Click Publish	Message can be set based on specified criteria / Create Post successfull	Message can be set based on specified criteria / Create Post successfull	Passed	No
Blast19			Positive	User Blast message with format Insert Links	User able to Blast message with format Insert Links	-Signin Google / -Click Group Soal A / -Choose Blast / -Put the title / -Set Message with format Insert Links / -Click Publish	Message can be set based on specified criteria / Create Post successfull	Message can be set based on specified criteria / Create Post successfull	Passed	No
Blast20			Positive	User Blast message with format More Rich	User able to Blast message with format More Rich	-Signin Google / -Click Group Soal A / -Choose Blast / -Put the title / -Set Message with format Imore Rich / -Click Publish	Message can be set based on specified criteria / Create Post successfull	Message can be set based on specified criteria / Create Post successfull	Passed	No
Blast21	Set Complete		Positive	User Complete the Post	User able to Complete the Post	-Signin Google / -Click Group Soal A / -Choose Blast / -Select Message Blast / -Click on the checkbox Complete this post / -Click Save	Set post complete successfull / Redirect to list Blast / Label completed display	Set post complete successfull / Redirect to list Blast / Label completed display	Passed	No
				Total Scenario	21
				Total Scenario Passed	18
				Total Scenario Failed	3
				Total Scenario Automated	4
				Total Scenario Running Manual	17
				Total Scenario Positive	18
				Total Scenario Negative	3

## Findings
Jira ID (#)	Defect Name	Priority	Step to Reproduce	Expected Result	Actual Result	PIC	Status	Detected Date	Closed Date	Type	Blocked Test Case	Remarks
Bug001	Loading Notifications never Stop	Normal	-Signin Google / -Click Icon Notifications	All Notifications displayed correctly	Intermittent Notification not displayed correctly	Tim Development	Open	25-Oct-2021
Bug002	User Edit Due Date but less than today	Normal	-Signin Google / -Click Group Soal A / -Click Board / -Select Card / -Select Edit Due Date / -Set the Date / -Set the Time / -Click Save Button	Due date cannot be less than today	Update Card is success	Tim Development	Open	25-Oct-2021								Bug Report Cicle App
Bug003	Blank Video after Downloaded in Group Chat	High	-Signin Google / -Click Group Soal A / -Click Group Chat / -Click Icon Attach / -Choose Video File	Success Send Message Group / Videos is display latest	Success Send Message Group / Videos display latest / Blank Video after Downloaded	Tim Development	Open	25-Oct-2021
Bug004	User publish blast but Due date less than today	High	-Signin Google / -Click Group Soal A / -Choose Blast / -Put the title / -Put the story / -set the Due Date less than today / -Click Publish	User not able publish blast but Due date less than today	Create Post successfull	Tim Development	Open	25-Oct-2021
Bug005	User succes publish blast but Title only space	Normal	-Signin Google / -Click Group Soal A / -Choose Blast / -Put the title space / -Click Publish	User not able publish blast but Title is space	Create Post successfull	Tim Development	Open	25-Oct-2021
Bug006	cccs	Normal	-Signin Google / -Click Group Soal A / -Choose Blast / -Select Blast with status complete / -Put the comment / -Click Save	User able to comment blast when blast is complete	Something When Wrong	Tim Development	Open	25-Oct-2021
								Total Findings	6
								Bug Priority Immadiate	0
								Bug Priority High	2
								Bug Priority Normal	4
								Bug Priority Low	0