## UAT Report
-- COPY THIS AREA IN THE ACK EMAIL BODY --
Cicle App
- Project Information - |  | - Test Result - |  |  |  | - Execution Plan - |  | - Actual Execution -
Report Date. | 23 Oktober 2021 | Status. |  |  |  | Start Date. | 2021-10-08 | Start Date. | 2021-10-08
Project No. |  | Completion. |  |  |  | Finish Date. | 23/10/2021 | Finish Date. | 23/10/2021
Test Cycle. |  | Total Test Case. | 105
Test Env. | Staging
- Total Results To Date -
Status. | Planned #. | Planned % | Actual #. | Actual % from Result to Date.
Plan. | 105 | 100%
Tested correctly |  |  | 101 | 96.19%
Tested with non Stopping Defect |  |  | 4 | 3.81%
Tested with Showstopper |  |  | 0 | 0%
In Progress |  |  | 0 | 0%
N/A |  |  | 0 | 0%
Not Tested |  |  | 0 | 0%
- Defect / Issue Details -
Defect ID (#) | Defect Name | Priority |  | PIC | Status | Detected Date | Closed Date | Type
Bug001 | Loading Notifications never Stop | Normal |  | Tim Development | Open | 2021-10-25 |  | ISSUE
Bug002 | User Edit Due Date but less than today | Normal |  | Tim Development | Open | 2021-10-25 |  | ISSUE
Bug003 | User attach the videos Group Chat | High |  | Tim Development | Open | 2021-10-25 |  | ISSUE
Bug004 | User publish blast but Due date less than today | High |  | Tim Development | Open | 2021-10-25 |  | ISSUE
Bug005 | User publish blast but Title is space | Normal |  | Tim Development | Open | 2021-10-25 |  | ISSUE
Bug006 | User comment blast when blast is complete | Normal |  | Tim Development | Open | 2021-10-25 |  | ISSUE
No. | Type. | Scenario ID | Scenario Case |  |  |  |  | Result. | Blocked by (Defect ID)
1 | Positve | Notif001 | User Check Notifications | User Check Notifications | User Check Notifications | User Check Notifications | User Check Notifications | Tested Correctly
2 | Positive | Notif002 | User click mark all read Notifications | User click mark all read Notifications | User click mark all read Notifications | User click mark all read Notifications | User click mark all read Notifications | Tested Correctly
3 | Positive | Notif003 | User view all Notifications | User view all Notifications | User view all Notifications | User view all Notifications | User view all Notifications | Tested Correctly
4 | Positive | Notif004 | User check Cheers Notifications | User check Cheers Notifications | User check Cheers Notifications | User check Cheers Notifications | User check Cheers Notifications | Tested Correctly
5 | Positive | Board01 | User Add Card Name | User Add Card Name | User Add Card Name | User Add Card Name | User Add Card Name | Tested Correctly
6 | Positive | Board02 | User Add Card with minimal 1 Char | User Add Card with minimal 1 Char | User Add Card with minimal 1 Char | User Add Card with minimal 1 Char | User Add Card with minimal 1 Char | Tested Correctly
7 | Positive | Board03 | User Add Card with numeric | User Add Card with numeric | User Add Card with numeric | User Add Card with numeric | User Add Card with numeric | Tested Correctly
8 | Positive | Board04 | User Add Card with special Char | User Add Card with special Char | User Add Card with special Char | User Add Card with special Char | User Add Card with special Char | Tested Correctly |  | -- COPY THIS AREA IN THE ACK EMAIL BODY --
9 | Negative | Board05 | User Add Card but Card Name empty | User Add Card but Card Name empty | User Add Card but Card Name empty | User Add Card but Card Name empty | User Add Card but Card Name empty | Tested Correctly
10 | Positive | Board06 | User Add Card but Enabling Private Card | User Add Card but Enabling Private Card | User Add Card but Enabling Private Card | User Add Card but Enabling Private Card | User Add Card but Enabling Private Card | Tested Correctly
11 | Positive | Board07 | User move card | User move card | User move card | User move card | User move card | Tested Correctly
12 | Positive | Board08 | User Quick Comment | User Quick Comment | User Quick Comment | User Quick Comment | User Quick Comment | Tested Correctly
13 | Positive | Board09 | User set the Members | User set the Members | User set the Members | User set the Members | User set the Members | Tested Correctly
14 | Positive | Board10 | User Edit Labels | User Edit Labels | User Edit Labels | User Edit Labels | User Edit Labels | Tested Correctly
15 | Positive | Board11 | User Edit Due Date | User Edit Due Date | User Edit Due Date | User Edit Due Date | User Edit Due Date | Tested Correctly
16 | Negative | Board12 | User Edit Due Date but less than today | User Edit Due Date but less than today | User Edit Due Date but less than today | User Edit Due Date but less than today | User Edit Due Date but less than today | Tested with non Stopping Defect
17 | Positive | Board13 | User Edit Notes | User Edit Notes | User Edit Notes | User Edit Notes | User Edit Notes | Tested Correctly
18 | Positive | Board14 | User Change Name | User Change Name | User Change Name | User Change Name | User Change Name | Tested Correctly
19 | Positive | Board15 | User Attach Files | User Attach Files | User Attach Files | User Attach Files | User Attach Files | Tested Correctly
20 | Positive | Board16 | User set Public/Private Card | User set Public/Private Card | User set Public/Private Card | User set Public/Private Card | User set Public/Private Card | Tested Correctly
21 | Positive | Board17 | User archive card | User archive card | User archive card | User archive card | User archive card | Tested Correctly
22 | Positive | Board18 | User archive all cards in this list | User archive all cards in this list | User archive all cards in this list | User archive all cards in this list | User archive all cards in this list | Tested Correctly
23 | Positive | Board19 | User archive this list | User archive this list | User archive this list | User archive this list | User archive this list | Tested Correctly
24 | Positive | Board20 | User set as a complete list | User set as a complete list | User set as a complete list | User set as a complete list | User set as a complete list | Tested Correctly
25 | Positive | Board21 | user sort this list from A to Z | user sort this list from A to Z | user sort this list from A to Z | user sort this list from A to Z | user sort this list from A to Z | Tested Correctly
26 | Positive | Board22 | user sort this list from Z to A | user sort this list from Z to A | user sort this list from Z to A | user sort this list from Z to A | user sort this list from Z to A | Tested Correctly
27 | Positive | Board23 | User sort this list by Nearest Due Date | User sort this list by Nearest Due Date | User sort this list by Nearest Due Date | User sort this list by Nearest Due Date | User sort this list by Nearest Due Date | Tested Correctly
28 | Positive | Board24 | User sort this list by Furthest Due Date | User sort this list by Furthest Due Date | User sort this list by Furthest Due Date | User sort this list by Furthest Due Date | User sort this list by Furthest Due Date | Tested Correctly
29 | Positive | Board25 | User sort this list by Nearest Created Date | User sort this list by Nearest Created Date | User sort this list by Nearest Created Date | User sort this list by Nearest Created Date | User sort this list by Nearest Created Date | Tested Correctly
30 | Positive | Board26 | User sort this list by Furthest Created Date | User sort this list by Furthest Created Date | User sort this list by Furthest Created Date | User sort this list by Furthest Created Date | User sort this list by Furthest Created Date | Tested Correctly
31 | Positive | Board27 | User search cards based on Label Colour | User search cards based on Label Colour | User search cards based on Label Colour | User search cards based on Label Colour | User search cards based on Label Colour | Tested Correctly
32 | Positive | Board28 | User search cards based on member | User search cards based on member | User search cards based on member | User search cards based on member | User search cards based on member | Tested Correctly
33 | Positive | Board29 | User search based on Due Soon | User search based on Due Soon | User search based on Due Soon | User search based on Due Soon | User search based on Due Soon | Tested Correctly
34 | Positive | Board30 | User search based on Due Today | User search based on Due Today | User search based on Due Today | User search based on Due Today | User search based on Due Today | Tested Correctly
35 | Positive | Board31 | User search based on Overdue | User search based on Overdue | User search based on Overdue | User search based on Overdue | User search based on Overdue | Tested Correctly
36 | Positive | Board32 | User unarchive Card | User unarchive Card | User unarchive Card | User unarchive Card | User unarchive Card | Tested Correctly
37 | Positive | Board33 | User unarchive list card | User unarchive list card | User unarchive list card | User unarchive list card | User unarchive list card | Tested Correctly
38 | Positive | Board34 | User comment the card | User comment the card | User comment the card | User comment the card | User comment the card | Tested Correctly
39 | Positive | Board35 | User Delete comment the card | User Delete comment the card | User Delete comment the card | User Delete comment the card | User Delete comment the card | Tested Correctly
40 | Positive | Board36 | User Edit Comment the card | User Edit Comment the card | User Edit Comment the card | User Edit Comment the card | User Edit Comment the card | Tested Correctly
41 | Positive | Board37 | User give Cheers | User give Cheers | User give Cheers | User give Cheers | User give Cheers | Tested Correctly
42 | Negative | Board38 | User give Cheers Empty | User give Cheers Empty | User give Cheers Empty | User give Cheers Empty | User give Cheers Empty | Tested Correctly
43 | Positive | Board39 | User Reply this comment | User Reply this comment | User Reply this comment | User Reply this comment | User Reply this comment | Tested Correctly
44 | Positive | Board40 | User Add to members from comment | User Add to members from comment | User Add to members from comment | User Add to members from comment | User Add to members from comment | Tested Correctly
45 | Positive | Board41 | User Add the labels from comment | User Add the labels from comment | User Add the labels from comment | User Add the labels from comment | User Add the labels from comment | Tested Correctly
46 | Positive | Board42 | User Edit the due date from comment | User Edit the due date from comment | User Edit the due date from comment | User Edit the due date from comment | User Edit the due date from comment | Tested Correctly
47 | Positive | Board43 | User Attach Files from comment | User Attach Files from comment | User Attach Files from comment | User Attach Files from comment | User Attach Files from comment | Tested Correctly
48 | Positive | Board44 | User Move Card from comment | User Move Card from comment | User Move Card from comment | User Move Card from comment | User Move Card from comment | Tested Correctly
49 | Positive | Board45 | User set Public Card from comment | User set Public Card from comment | User set Public Card from comment | User set Public Card from comment | User set Public Card from comment | Tested Correctly
50 | Positive | Board46 | User Archive Card from comment | User Archive Card from comment | User Archive Card from comment | User Archive Card from comment | User Archive Card from comment | Tested Correctly
51 | Positive | Board47 | User Edit Notes from comment | User Edit Notes from comment | User Edit Notes from comment | User Edit Notes from comment | User Edit Notes from comment | Tested Correctly
52 | Positive | Board48 | User Edit Comment with format Bold | User Edit Comment with format Bold | User Edit Comment with format Bold | User Edit Comment with format Bold | User Edit Comment with format Bold | Tested Correctly
53 | Positive | Board49 | User Edit Comment with format Italic | User Edit Comment with format Italic | User Edit Comment with format Italic | User Edit Comment with format Italic | User Edit Comment with format Italic | Tested Correctly
54 | Positive | Board50 | User Edit Comment with format Strikethrough | User Edit Comment with format Strikethrough | User Edit Comment with format Strikethrough | User Edit Comment with format Strikethrough | User Edit Comment with format Strikethrough | Tested Correctly
55 | Positive | Board51 | User Edit Comment with format Background Colour | User Edit Comment with format Background Colour | User Edit Comment with format Background Colour | User Edit Comment with format Background Colour | User Edit Comment with format Background Colour | Tested Correctly
56 | Positive | Board52 | User Edit Comment with format Font Size | User Edit Comment with format Font Size | User Edit Comment with format Font Size | User Edit Comment with format Font Size | User Edit Comment with format Font Size | Tested Correctly
57 | Positive | Board53 | User Edit Comment with format More text | User Edit Comment with format More text | User Edit Comment with format More text | User Edit Comment with format More text | User Edit Comment with format More text | Tested Correctly
58 | Positive | Board54 | User Edit Comment with format Ordered List | User Edit Comment with format Ordered List | User Edit Comment with format Ordered List | User Edit Comment with format Ordered List | User Edit Comment with format Ordered List | Tested Correctly
59 | Positive | Board55 | User Edit Comment with format unordered List | User Edit Comment with format unordered List | User Edit Comment with format unordered List | User Edit Comment with format unordered List | User Edit Comment with format unordered List | Tested Correctly
60 | Positive | Board56 | User Edit Comment with format unordered More Paragraph | User Edit Comment with format unordered More Paragraph | User Edit Comment with format unordered More Paragraph | User Edit Comment with format unordered More Paragraph | User Edit Comment with format unordered More Paragraph | Tested Correctly
61 | Positive | Board57 | User Edit Comment with format Emoticon | User Edit Comment with format Emoticon | User Edit Comment with format Emoticon | User Edit Comment with format Emoticon | User Edit Comment with format Emoticon | Tested Correctly
62 | Positive | Board58 | User Edit Comment with format Files | User Edit Comment with format Files | User Edit Comment with format Files | User Edit Comment with format Files | User Edit Comment with format Files | Tested Correctly
63 | Positive | Board59 | User Edit Comment with format Insert Links | User Edit Comment with format Insert Links | User Edit Comment with format Insert Links | User Edit Comment with format Insert Links | User Edit Comment with format Insert Links | Tested Correctly
64 | Positive | Board60 | User Edit Comment with format More Rich | User Edit Comment with format More Rich | User Edit Comment with format More Rich | User Edit Comment with format More Rich | User Edit Comment with format More Rich | Tested Correctly
65 | Positive | GroupChat01 | User send Message is String Group Chat |  |  |  |  | Tested Correctly
66 | Positive | GroupChat02 | User send Message is Numeric Group Chat |  |  |  |  | Tested Correctly
67 | Positive | GroupChat03 | User send Message is Numeric Group Chat |  |  |  |  | Tested Correctly
68 | Positive | GroupChat04 | User send Message is GSM 7 Character Group Chat |  |  |  |  | Tested Correctly
69 | Positive | GroupChat05 | User send Message is UTF 8 Character Group Chat |  |  |  |  | Tested Correctly
70 | Positive | GroupChat06 | User send Message is Unicode Character Group Chat |  |  |  |  | Tested Correctly
71 | Positive | GroupChat07 | User send File Screenshots Group Chat |  |  |  |  | Tested Correctly
72 | Negative | GroupChat08 | User send File CSV Screenshots Group Chat |  |  |  |  | Tested Correctly
73 | Negative | GroupChat09 | User send File APK Group Chat |  |  |  |  | Tested Correctly
74 | Positive | GroupChat10 | User send File XLS Group Chat |  |  |  |  | Tested Correctly
75 | Positive | GroupChat11 | User send File Doc Screenshots Group Chat |  |  |  |  | Tested Correctly
76 | Positive | GroupChat12 | User send File PDF Screenshots Group Chat |  |  |  |  | Tested Correctly
77 | Positive | GroupChat13 | User send URL Group Chat |  |  |  |  | Tested Correctly
78 | Positive | GroupChat14 | User send messages 5000 char Group Chat |  |  |  |  | Tested Correctly
79 | Positive | GroupChat15 | User attach the videos Group Chat |  |  |  |  | Tested Correctly
80 | Positive | GroupChat16 | User attach the videos Maximum File Size Group Chat |  |  |  |  | Tested Correctly
81 | Negative | GroupChat17 | User send messages empty Group Chat |  |  |  |  | Tested Correctly
82 | Positive | GroupChat18 | User delete the chat |  |  |  |  | Tested Correctly
83 | Positive | GroupChat19 | User change Photo Profile from Group Chat |  |  |  |  | Tested Correctly
84 | Positive | GroupChat20 | User change Name Profile |  |  |  |  | Tested Correctly
85 | Positive | Blast01 | User publish blast |  |  |  |  | Tested Correctly
86 | Positive | Blast02 | User publish blast with title emoticon |  |  |  |  | Tested Correctly
87 | Negative | Blast03 | User publish blast but Due date less than today |  |  |  |  | Tested with non Stopping Defect
88 | Negative | Blast04 | User publish blast but Title is space |  |  |  |  | Tested with non Stopping Defect
89 | Positive | Blast05 | User comment blast when blast is complete |  |  |  |  | Tested with non Stopping Defect
90 | Negative | Blast06 | User publish blast but all mandatory empty |  |  |  |  | Tested Correctly
91 | Positive | Blast07 | User publish with set Notified |  |  |  |  | Tested Correctly
92 | Positive | Blast08 | User Blast message with format Bold |  |  |  |  | Tested Correctly
93 | Positive | Blast09 | User Blast message with format Italic |  |  |  |  | Tested Correctly
94 | Positive | Blast10 | User Blast message with format Strikethrough |  |  |  |  | Tested Correctly
95 | Positive | Blast11 | User Blast message with format Background Colour |  |  |  |  | Tested Correctly
96 | Positive | Blast12 | User Blast message with format Font Size |  |  |  |  | Tested Correctly
97 | Positive | Blast13 | User Blast message with format More text |  |  |  |  | Tested Correctly
98 | Positive | Blast14 | User Blast message with format Ordered List |  |  |  |  | Tested Correctly
99 | Positive | Blast15 | User Blast message with format unordered List |  |  |  |  | Tested Correctly
100 | Positive | Blast16 | User Blast message with format unordered More Paragraph |  |  |  |  | Tested Correctly
101 | Positive | Blast17 | User Blast message with format Emoticon |  |  |  |  | Tested Correctly
102 | Positive | Blast18 | User Blast message with format Files |  |  |  |  | Tested Correctly
103 | Positive | Blast19 | User Blast message with format Insert Links |  |  |  |  | Tested Correctly
104 | Positive | Blast20 | User Blast message with format More Rich |  |  |  |  | Tested Correctly
105 | Positive | Blast21 | User Complete the Post |  |  |  |  | Tested Correctly

## UAT Scenario
No | Scenario ID | Scenario Cases | Feature | Involved System or Application | Scenario Type | Planned Date | Execution Date | Status | Tester | Notes
1 | Notif001 | User Check Notifications | Notifications | Cicle | Positve | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
2 | Notif002 | User click mark all read Notifications | Notifications | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
3 | Notif003 | User view all Notifications | Notifications | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
4 | Notif004 | User check Cheers Notifications | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
5 | Board01 | User Add Card Name | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
6 | Board02 | User Add Card with minimal 1 Char | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
7 | Board03 | User Add Card with numeric | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
8 | Board04 | User Add Card with special Char | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
9 | Board05 | User Add Card but Card Name empty | Board | Cicle | Negative | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
10 | Board06 | User Add Card but Enabling Private Card | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
11 | Board07 | User move card | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
12 | Board08 | User Quick Comment | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
13 | Board09 | User set the Members | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
14 | Board10 | User Edit Labels | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
15 | Board11 | User Edit Due Date | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
16 | Board12 | User Edit Due Date but less than today | Board | Cicle | Negative | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
17 | Board13 | User Edit Notes | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
18 | Board14 | User Change Name | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
19 | Board15 | User Attach Files | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
20 | Board16 | User set Public/Private Card | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
21 | Board17 | User archive card | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
22 | Board18 | User archive all cards in this list | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
23 | Board19 | User archive this list | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
24 | Board20 | User set as a complete list | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
25 | Board21 | user sort this list from A to Z | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
26 | Board22 | user sort this list from Z to A | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
27 | Board23 | User sort this list by Nearest Due Date | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
28 | Board24 | User sort this list by Furthest Due Date | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
29 | Board25 | User sort this list by Nearest Created Date | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
30 | Board26 | User sort this list by Furthest Created Date | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
31 | Board27 | User search cards based on Label Colour | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
32 | Board28 | User search cards based on member | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
33 | Board29 | User search based on Due Soon | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
34 | Board30 | User search based on Due Today | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
35 | Board31 | User search based on Overdue | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
36 | Board32 | User unarchive Card | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
37 | Board33 | User unarchive list card | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
38 | Board34 | User comment the card | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
39 | Board35 | User Delete comment the card | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
40 | Board36 | User Edit Comment the card | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
41 | Board37 | User give Cheers | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
42 | Board38 | User give Cheers Empty | Board | Cicle | Negative | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
43 | Board39 | User Reply this comment | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
44 | Board40 | User Add to members from comment | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
45 | Board41 | User Add the labels from comment | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
46 | Board42 | User Edit the due date from comment | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
47 | Board43 | User Attach Files from comment | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
48 | Board44 | User Move Card from comment | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
49 | Board45 | User set Public Card from comment | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
50 | Board46 | User Archive Card from comment | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
51 | Board47 | User Edit Notes from comment | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
52 | Board48 | User Edit Comment with format Bold | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
53 | Board49 | User Edit Comment with format Italic | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
54 | Board50 | User Edit Comment with format Strikethrough | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
55 | Board51 | User Edit Comment with format Background Colour | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
56 | Board52 | User Edit Comment with format Font Size | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
57 | Board53 | User Edit Comment with format More text | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
58 | Board54 | User Edit Comment with format Ordered List | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
59 | Board55 | User Edit Comment with format unordered List | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
60 | Board56 | User Edit Comment with format unordered More Paragraph | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
61 | Board57 | User Edit Comment with format Emoticon | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
62 | Board58 | User Edit Comment with format Files | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
63 | Board59 | User Edit Comment with format Insert Links | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
64 | Board60 | User Edit Comment with format More Rich | Board | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
65 | GroupChat01 | User send Message is String Group Chat | Group Chat | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
66 | GroupChat02 | User send Message is Numeric Group Chat | Group Chat | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
67 | GroupChat03 | User send Message is Numeric Group Chat | Group Chat | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
68 | GroupChat04 | User send Message is GSM 7 Character Group Chat | Group Chat | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
69 | GroupChat05 | User send Message is UTF 8 Character Group Chat | Group Chat | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
70 | GroupChat06 | User send Message is Unicode Character Group Chat | Group Chat | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
71 | GroupChat07 | User send File Screenshots Group Chat | Group Chat | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
72 | GroupChat08 | User send File CSV Screenshots Group Chat | Group Chat | Cicle | Negative | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
73 | GroupChat09 | User send File APK Group Chat | Group Chat | Cicle | Negative | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
74 | GroupChat10 | User send File XLS Group Chat | Group Chat | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
75 | GroupChat11 | User send File Doc Screenshots Group Chat | Group Chat | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
76 | GroupChat12 | User send File PDF Screenshots Group Chat | Group Chat | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
77 | GroupChat13 | User send URL Group Chat | Group Chat | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
78 | GroupChat14 | User send messages 5000 char Group Chat | Group Chat | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
79 | GroupChat15 | User attach the videos Group Chat | Group Chat | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
80 | GroupChat16 | User attach the videos Maximum File Size Group Chat | Group Chat | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
81 | GroupChat17 | User send messages empty Group Chat | Group Chat | Cicle | Negative | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
82 | GroupChat18 | User delete the chat | Group Chat | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
83 | GroupChat19 | User change Photo Profile from Group Chat | Group Chat | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
84 | GroupChat20 | User change Name Profile | Group Chat | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
85 | Blast01 | User publish blast | Blast01 | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
86 | Blast02 | User publish blast with title emoticon | Blast02 | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
87 | Blast03 | User publish blast but Due date less than today | Blast03 | Cicle | Negative | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
88 | Blast04 | User publish blast but Title is space | Blast04 | Cicle | Negative | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
89 | Blast05 | User comment blast when blast is complete | Blast05 | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
90 | Blast06 | User publish blast but all mandatory empty | Blast06 | Cicle | Negative | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
91 | Blast07 | User publish with set Notified | Blast07 | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
92 | Blast08 | User Blast message with format Bold | Blast08 | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
93 | Blast09 | User Blast message with format Italic | Blast09 | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
94 | Blast10 | User Blast message with format Strikethrough | Blast10 | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
95 | Blast11 | User Blast message with format Background Colour | Blast11 | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
96 | Blast12 | User Blast message with format Font Size | Blast12 | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
97 | Blast13 | User Blast message with format More text | Blast13 | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
98 | Blast14 | User Blast message with format Ordered List | Blast14 | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
99 | Blast15 | User Blast message with format unordered List | Blast15 | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
100 | Blast16 | User Blast message with format unordered More Paragraph | Blast16 | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
101 | Blast17 | User Blast message with format Emoticon | Blast17 | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
102 | Blast18 | User Blast message with format Files | Blast18 | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
103 | Blast19 | User Blast message with format Insert Links | Blast19 | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
104 | Blast20 | User Blast message with format More Rich | Blast20 | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty
105 | Blast21 | User Complete the Post | Blast21 | Cicle | Positive | 08-10-2021 | 23-10-2021 | Tested Correctly | Arisa Hazriaty

## Cases - Notifications
Test Case ID | Feature | Precondition | Positive/Negative | Scenario Name | Test Case Objective | Test Step | Expected Behaviour | Actual Behaviour | Result | Automated | Bug-ID
Notif001 | Check Notif | User open the Boards | Positive | User Check Notifications | User able to Check All Notifications | -Signin Google -Click Icon Notifications | All Notifications Display Reminder Notification will hide | All Notifications Display Reminder Notification will hide | Passed | No
Notif002 |  |  | Positive | User click mark all read Notifications | User able to click mark all read Notifications | -Signin Google -Click Mark all read Notifications | Update mark read notification and activities successful | Update mark read notification and activities successful | Passed | No
Notif003 |  |  | Positive | User view all Notifications | User able to view all Notifications | -Signin Google -View All Notification | All Notifications Display | All Notifications Display | Passed | No
Notif004 |  |  | Positive | User check Cheers Notifications | User able to check Cheers Notifications | -Signin Google -Click Cheers | All Cheers Display | All Cheers Display | Passed | No
[9 empty] | Total Scenario | 4
[9 empty] | Total Scenario Passed | 4
[9 empty] | Total Scenario Failed | 0
[9 empty] | Total Scenario Automated | 0
[9 empty] | Total Scenario Running Manual | 4
[9 empty] | Total Scenario Positive | 4
[9 empty] | Total Scenario Negative | 0

## Cases - Feature Board
Test Case ID | Feature | Precondition | Positive/Negative | Scenario Name | Test Case Objective | Test Step | Expected Behaviour | Actual Behaviour | Result | Automated | Bug-ID
Board01 | Add Card | User open the Boards | Positive | User Add Card Name | User able to add Card | -Signin Google -Click Group Soal A -Click Board -Select List Action -Click Icon Add Card -Set the card name -Click Add Card Button | Creating card is success Card display on board | Creating card is success Card display on board | Passed | Yes
Board02 |  |  | Positive | User Add Card with minimal 1 Char | User able to Add Card with minimal 1 Char | -Signin Google -Click Group Soal A -Click Board -Select List Action -Click Icon Add Card -Set the card name -Click Add Card Button | Creating card is success Card display on board | Creating card is success Card display on board | Passed | No
Board03 |  |  | Positive | User Add Card with numeric | User able to Add Card with minimal 1 Char | -Signin Google -Click Group Soal A -Click Board -Select List Action -Click Icon Add Card -Set the card 1 char -Click Add Card Button | Creating card is success Card display on board | Creating card is success Card display on board | Passed | No
Board04 |  |  | Positive | User Add Card with special Char | User able to Add Card with special Char | -Signin Google -Click Group Soal A -Click Board -Select List Action -Click Icon Add Card -Set the card with special Char -Click Add Card Button | Creating card is success Card display on board | Creating card is success Card display on board | Passed | No
Board05 |  |  | Negative | User Add Card but Card Name empty | User able to add Card | -Signin Google -Click Group Soal A -Click Board -Select List Action -Click Icon Add Card -Set the card name Empty -Click Add Card Button | Card name cannot be empty | Card name cannot be empty | Passed | Yes
Board06 |  |  | Positive | User Add Card but Enabling Private Card | User able to Add Card but Enabling Private Card | -Signin Google -Click Group Soal A -Click Board -Select List Action -Click Icon Add Card -Set the card name - Set Private Card is on - Click Add Card Button | Creating card is success Card display on board | Creating card is success Card display on board | Passed | Yes
Board07 | Move Card |  | Positive | User move card | User able to move card | -Signin Google -Click Group Soal A -Click Board -Select Card -Select Move Card -Select list board -Click Move | Move card is success Card is moved and display | Move card is success Card is moved and display | Passed | Yes
Board08 |  |  | Positive | User Quick Comment | User able to Add Quick Comment | -Signin Google -Click Group Soal A -Click Board -Select Card -Select Quick Comment -Add New Comment -Input Comment -Click Save | Create comment is success Comment displayed on top | Create comment is success Comment displayed on top | Passed | Yes
Board09 |  |  | Positive | User set the Members | User set the Members | -Signin Google -Click Group Soal A -Click Board -Select Card -Select Change Members -Set Team Members -Click icon close | Toogle member card is success | Toogle member card is success | Passed | No
Board10 |  |  | Positive | User Edit Labels | User able to add Labels | -Signin Google -Click Group Soal A -Click Board -Select Card -Select Edit Labels -Create New Label -Input Name -Select Color - Click Create Button | Creating label for this board is success Label selected is displayed | Creating label for this board is success Label selected is displayed | Passed | No
Board11 |  |  | Positive | User Edit Due Date | User able to edit Due Date | -Signin Google -Click Group Soal A -Click Board -Select Card -Select Edit Due Date -Set the Date -Set the Time -Click Save Button | Update Card is success | Update Card is success | Passed | Yes
Board12 |  |  | Negative | User Edit Due Date but less than today | User not able to Edit Due Date but less than today | -Signin Google -Click Group Soal A -Click Board -Select Card -Select Edit Due Date -Set the Date -Set the Time -Click Save Button | Due date cannot be less than today | Update Card is success | Failed | No
Board13 |  |  | Positive | User Edit Notes | User able to edit Notes | -Signin Google -Click Group Soal A -Click Board -Select Card -Select Edit Notes -Input Notes -Click Save Button | Update Card is success | Update Card is success | Passed | Yes
Board14 |  |  | Positive | User Change Name | User able to change name card | -Signin Google -Click Group Soal A -Click Board -Select Card -Select Change Name -Edit Card Name -Click Save Button | Update Card is success | Update Card is success | Passed | Yes
Board15 |  |  | Positive | User Attach Files | User able to attach Files | -Signin Google -Click Group Soal A -Click Board -Select Card -Select Attach Files -Choose File | Upload attachment is success File attachment is displayed | Upload attachment is success File attachment is displayed | Passed | No
Board16 |  |  | Positive | User set Public/Private Card | User able to set Public/Private Card | -Signin Google -Click Group Soal A -Click Board -Select Card -Set Public/Private Card | Upload attachment is success Icon Public/Private card is displayed | Upload attachment is success Icon Public/Private card is displayed | Passed | No
Board17 |  |  | Positive | User archive card | User able to archive card | -Signin Google -Click Group Soal A -Click Board -Select Card -Select Archive | Archiving card is success Card is hidden | Archiving card is success Card is hidden | Passed | No
Board18 | List Action |  | Positive | User archive all cards in this list | User able to archive all cards in this list | -Signin Google -Click Group Soal A -Click Board -Select Card -Select Archive All cards in this list | Archive card is success All Card is hidden | Archiving card is success Card is hidden | Passed | No
Board19 |  |  | Positive | User archive this list | User able to archive this list | -Signin Google -Click Group Soal A -Click Board -Select Card -Select Archive this list | Archive list this card is success | Archive list this card is success | Passed | No
Board20 |  |  | Positive | User set as a complete list | User able to set as a complete list | -Signin Google -Click Group Soal A -Click Board -Select Card -Select Set as a Complete list | Set list as Complete is success | Set list as Complete is success | Passed | No
Board21 |  |  | Positive | user sort this list from A to Z | User able to sort list from A to Z | -Signin Google -Click Group Soal A -Click Board -Select Card -Select sort this list from A to Z | Sort this list from A to Z is success | Sort this list from A to Z is success | Passed | No
Board22 |  |  | Positive | user sort this list from Z to A | User able to sort list from Z to A | -Signin Google -Click Group Soal A -Click Board -Select Card -Select sort this list from A to Z | Sort this list from Z to A is success | Sort this list from Z to A is success | Passed | No
Board23 |  |  | Positive | User sort this list by Nearest Due Date | User able to this list by Nearest Due Date | -Signin Google -Click Group Soal A -Click Board -Select Card -Select Sort list by Nearest Due Date | Sort list by Nearest Due Date is success | Sort list by Nearest Due Date is success | Passed | No
Board24 |  |  | Positive | User sort this list by Furthest Due Date | User able to sort this list by Furthest Due Date | -Signin Google -Click Group Soal A -Click Board -Select Card -Select Sort list by Furthest Due Date | Sort list by Furthest Due Date is success | Sort list by Furthest Due Date is success | Passed | No
Board25 |  |  | Positive | User sort this list by Nearest Created Date | User able to sort this list by Nearest Created Date | -Signin Google -Click Group Soal A -Click Board -Select Card -Select Sort list by Nearest Created Date | Sort list by Nearest Created Date is success | Sort list by Nearest Created Date is success | Passed | No
Board26 |  |  | Positive | User sort this list by Furthest Created Date | User able to sort this list by Furthest Created Date | -Signin Google -Click Group Soal A -Click Board -Select Card -Select list by Furthest Created | Sort list by Furthest Created Date is success | Sort list by Furthest Created Date is success | Passed | No
Board27 | Search Cards |  | Positive | User search cards based on Label Colour | User able to search cards based on Label Colour | -Signin Google -Click Group Soal A -Click Board -Click Icon search -Select the label | Search based on label color is displayed | Search based on label color is displayed | Passed | No
Board28 |  |  | Positive | User search cards based on member | User able to search cards based on member | -Signin Google -Click Group Soal A -Click Board -Click Icon search -Select member | Search based on member is displayed | Search based on member is displayed | Passed | No
Board29 |  |  | Positive | User search based on Due Soon | User able to search based on Due Soon | -Signin Google -Click Group Soal A -Click Board -Click Icon search -Select Due Soon | Search based on Due Soon is displayed | Search based on Due Soon is displayed | Passed | No
Board30 |  |  | Positive | User search based on Due Today | User able to search based on Due Today | -Signin Google -Click Group Soal A -Click Board -Click Icon search -Select Due Today | Search based on Due Today is displayed | Search based on Due Today is displayed | Passed | No
Board31 |  |  | Positive | User search based on Overdue | User able to search based on Overdue | -Signin Google -Click Group Soal A -Click Board -Click Icon search -Select Overdue | Search based on Overdue is displayed | Search based on Overdue is displayed | Passed | No
Board32 | Unarchive Cards |  | Positive | User unarchive Card | User able to unarchive items | -Signin Google -Click Group Soal A -Click Board -Click Icon Archived Items -Search Cards -Click Restore | Unarchiving card is success | Unarchiving card is success | Passed | No
Board33 | Unarchive list cards |  | Positive | User unarchive list card | User able to unarchive list card | -Signin Google -Click Group Soal A -Click Board -Click Icon Archived Items -Click Switch to lists -Select list card -Click Restore | Unarchiving list with card is success | Unarchiving list with card is success | Passed | Yes
Board34 | Comment Card |  | Positive | User comment the card | User able to comment the card | -Signin Google -Click Group Soal A -Click Board -Select Card -Click icon Comment -Put the comment -Click Save Button | Create comment is success | Create comment is success | Passed | Yes
Board35 |  |  | Positive | User Delete comment the card | User able to Delete comment the card | -Signin Google -Click Group Soal A -Click Board -Select Card -Click icon Comment -Select comment will be deleted -Click Delete Button | Delete Comment is success | Delete Comment is success | Passed | No
Board36 |  |  | Positive | User Edit Comment the card | User able to Edit Comment the card | -Signin Google -Click Group Soal A -Click Board -Select Card -Click icon Comment -Select comment will be edit -Set the Comment -Click Save Button | Update Comment is success | Update Comment is success | Passed | No
Board37 |  |  | Positive | User give Cheers | User able to give Cheers | -Signin Google -Click Group Soal A -Click Board -Select Card -Click icon Comment -Click Icon Cheers -Put the cheers -Click Icon Checklist | Create cheers on card comment successfull | Create cheers on card comment successfull | Passed | No
Board38 |  |  | Negative | User give Cheers Empty | User not able to give Cheers Empty | -Signin Google -Click Group Soal A -Click Board -Select Card -Click icon Comment -Click Icon Cheers -Put the cheers empty -Click Icon Checklist | Cheer cannot be empty | Cheer cannot be empty | Passed | No
Board39 |  |  | Positive | User Reply this comment | User able to Reply this comment | -Signin Google -Click Group Soal A -Click Board -Select Card -Click icon Comment -Select Comment -Put New Comment -Click Icon Checklist | Create discussion on card moment successfull | Create discussion on card moment successfull | Passed | No
Board40 |  |  | Positive | User Add to members from comment | User able to Add member from feature comment | -Signin Google -Click Group Soal A -Click Board -Select Card -Click icon Comment -Select icon Add Members -Set the members | Toogle member card is success | Toogle member card is success | Passed | No
Board41 |  |  | Positive | User Add the labels from comment | User able to Add the labels | -Signin Google -Click Group Soal A -Click Board -Select Card -Click icon Comment -Select icon labels -Set The label/Create | Creating label for this board is success Label selected is displayed | Creating label for this board is success Label selected is displayed | Passed | No
Board42 |  |  | Positive | User Edit the due date from comment | User able to Edit the due date | -Signin Google -Click Group Soal A -Click Board -Select Card -Click icon Comment -Select icon Due Date -Set the date -Click Save Button | Update Card is success | Update Card is success | Passed | No
Board43 |  |  | Positive | User Attach Files from comment | User able to Attached Files from comment | -Signin Google -Click Group Soal A -Click Board -Select Card -Click icon Comment -Select Attach File -Choose file -Click Open | Upload attachment is success File attachment is displayed | Upload attachment is success File attachment is displayed | Passed | No
Board44 |  |  | Positive | User Move Card from comment | User able to Move Card from comment | -Signin Google -Click Group Soal A -Click Board -Select Card -Click icon move card -Select the list -Click Move Button | Move card is success Card is moved and display | Move card is success Card is moved and display | Passed | Yes
Board45 |  |  | Positive | User set Public Card from comment | User able to set Public Card from comment | -Signin Google -Click Group Soal A -Click Board -Select Card -Click icon Public/Private Card | Update Card is success Icon Public/Private card is displayed | Update Card is success Icon Public/Private card is displayed | Passed | No
Board46 |  |  | Positive | User Archive Card from comment | User able to Archive Card from comment | -Signin Google -Click Group Soal A -Click Board -Select Card -Click icon Archiving Card | Archiving card is success Icon Archiving card is hidden | Archiving card is success Icon Archiving card is hidden | Passed | No
Board47 |  |  | Positive | User Edit Notes from comment | User able to Edit Notes from comment | -Signin Google -Click Group Soal A -Click Board -Select Card -Click icon edit comment -Click Save Button | Update Card is success Notes display latest update | Update Card is success Notes display latest update | Passed | No
Board48 | Add/Edit Comment |  | Positive | User Edit Comment with format Bold | User able to Edit Comment with format Bold | -Signin Google -Click Group Soal A -Click Board -Select Card -Set Comment with format Bold -Click Save | Comment can be set based on specified criteria Add/Edit Comment successfull | Comment can be set based on specified criteria Add/Edit Comment successfull | Passed | No
Board49 |  |  | Positive | User Edit Comment with format Italic | User able to Edit Comment with format Italic | -Signin Google -Click Group Soal A -Click Board -Select Card -Set Comment with format Italic -Click Save | Comment can be set based on specified criteria Add/Edit Comment successfull | Comment can be set based on specified criteria Add/Edit Comment successfull | Passed | No
Board50 |  |  | Positive | User Edit Comment with format Strikethrough | User able to Edit Comment with format Strikethrough | -Signin Google -Click Group Soal A -Click Board -Select Card -Set Comment with format Strikethrough -Click Save | Comment can be set based on specified criteria Add/Edit Comment successfull | Comment can be set based on specified criteria Add/Edit Comment successfull | Passed | No
Board51 |  |  | Positive | User Edit Comment with format Background Colour | User able to Edit Comment with format Background Colour | -Signin Google -Click Group Soal A -Choose Blast -Put the title -Set Message with format Background Color -Click Publish | Comment can be set based on specified criteria Add/Edit Comment successfull | Comment can be set based on specified criteria Add/Edit Comment successfull | Passed | No
Board52 |  |  | Positive | User Edit Comment with format Font Size | User able to Edit Comment with format Font Size | -Signin Google -Click Group Soal A -Click Board -Select Card -Set Message with format Font Size -Click Save | Comment can be set based on specified criteria Add/Edit Comment successfull | Comment can be set based on specified criteria Add/Edit Comment successfull | Passed | No
Board53 |  |  | Positive | User Edit Comment with format More text | User able to Edit Comment with format More text | -Signin Google -Click Group Soal A -Click Board -Select Card -Set Comment with format More Text -Click Save | Comment can be set based on specified criteria Add/Edit Comment successfull | Comment can be set based on specified criteria Add/Edit Comment successfull | Passed | No
Board54 |  |  | Positive | User Edit Comment with format Ordered List | User able to Edit Comment with format Ordered List | -Signin Google -Click Group Soal A -Click Board -Select Card -Set Comment with format Ordered List -Click Publish | Comment can be set based on specified criteria Add/Edit Comment successfull | Comment can be set based on specified criteria Add/Edit Comment successfull | Passed | No
Board55 |  |  | Positive | User Edit Comment with format unordered List | User able to Edit Comment with format unordered List | -Signin Google -Click Group Soal A -Click Board -Select Card -Set Comment with format unordered List -Click Save | Comment can be set based on specified criteria Add/Edit Comment successfull | Comment can be set based on specified criteria Add/Edit Comment successfull | Passed | No
Board56 |  |  | Positive | User Edit Comment with format unordered More Paragraph | User able to Edit Comment with format More Paragraph | -Signin Google -Click Group Soal A -Click Board -Select Card -Set Comment with format More paragraph -Click Save | Comment can be set based on specified criteria Add/Edit Comment successfull | Comment can be set based on specified criteria Add/Edit Comment successfull | Passed | No
Board57 |  |  | Positive | User Edit Comment with format Emoticon | User able to Edit Comment with format Emoticon | -Signin Google -Click Group Soal A -Click Board -Select Card -Set Comment with format Emoticon -Click Save | Comment can be set based on specified criteria Add/Edit Comment successfull | Comment can be set based on specified criteria Add/Edit Comment successfull | Passed | No
Board58 |  |  | Positive | User Edit Comment with format Files | User able to Edit Comment with format Files | -Signin Google -Click Group Soal A -Click Board -Select Card -Set Message with format Files -Click Save | Comment can be set based on specified criteria Add/Edit Comment successfull | Comment can be set based on specified criteria Add/Edit Comment successfull | Passed | No
Board59 |  |  | Positive | User Edit Comment with format Insert Links | User able to Edit Comment with format Insert Links | -Signin Google -Click Group Soal A -Click Board -Select Card -Set Message with format Insert Links -Click Save | Comment can be set based on specified criteria Add/Edit Comment successfull | Comment can be set based on specified criteria Add/Edit Comment successfull | Passed | No
Board60 |  |  | Positive | User Edit Comment with format More Rich | User able to Edit Comment with format More Rich | -Signin Google -Click Group Soal A -Click Board -Select Card -Set Message with format Imore Rich -Click Save | Comment can be set based on specified criteria Add/Edit Comment successfull | Comment can be set based on specified criteria Add/Edit Comment successfull | Passed | No
[9 empty] | Total Scenario | 60
[9 empty] | Total Scenario Passed | 59
[9 empty] | Total Scenario Failed | 1
[9 empty] | Total Scenario Automated | 11
[9 empty] | Total Scenario Running Manual | 49
[9 empty] | Total Scenario Positive | 57
[9 empty] | Total Scenario Negative | 3

## UAT Report (hidden)
Two Wheelers EFP
- Project Information - |  | - Test Result - |  |  |  | - Execution Plan - |  | - Actual Execution -
Report Date. | 2021-10-23 | Status. | OK |  |  | Start Date. | 0 | Start Date. | 0
Project No. | UAT | Completion. | 100% Tested Correctly / 100% Executed |  |  | Finish Date. | 0 | Finish Date. | 0
Test Env. | C1 | Total Test Case. | 91
- Total Results To Date -
Status. | Planned #. | Planned % | Actual #. | Actual % from Result to Date.
Plan. | 100 | 100% | 100 | 100%
Tested correctly | 100 | 100% | 100 | 100%
Tested with non Stopping Defect |  |  | 0 | 0%
Tested with Showstopper |  |  | 0 | 0%
In Progress |  |  | 0 | 0%
N/A |  |  | 0 | 0%
Not Tested |  |  | 0 | 0%
- Defect / Issue Details -
Defect ID (#) | Defect Name | Description |  | PIC | Status | Detected Date | Closed Date | Type | Blocked Test Case
Bug001 | Loading Notifications never Stop | Normal |  | All Notifications displayed correctly | Open | 2021-10-25 | 0 | 0 | 0
#REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
No. | Type. | Scenario ID | Scenario Case |  |  |  |  | Result.
1 | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | #VALUE!
2 | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | #VALUE!
3 | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | #VALUE!
4 | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | #VALUE!
5 | Positive | User Change Name | #VALUE! |  |  |  |  | Tested Correctly
6 | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | #VALUE!
7 | #VALUE! | User Attach Files | #VALUE! |  |  |  |  | #VALUE!
8 | Positive | #VALUE! | user sort this list from A to Z |  |  |  |  | Tested Correctly
9 | #REF! | User set Public/Private Card | #VALUE! |  |  |  |  | #REF!
10 | #REF! | User archive card | #VALUE! |  |  |  |  | #REF!
11 | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | #VALUE!
12 | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | #VALUE!
13 | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | #VALUE!
14 | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | #VALUE!

## SIT Scenario (hidden)
No | Scenario ID | Scenario Cases | Product Code | Involved System or Application | Pre Condition | Scenario Type | Planned Date | Execution Date | Status | Tester | Notes

## Reff Table (hidden)
Test Cycle | Test Env | Progress / Result | Test Priority | Scenario Type | Status | Defect / Issue | Defect Status
SIT | C1 | OK | High | Positive | Tested correctly | DEFECT | Open
| PreProd | OK | High | Positive | Tested correctly | DEFECT | Open
UAT | C2 | NOT OK | Medium | Negative | Tested with non Stopping Defect | ISSUE | In Progress
| C3 | In Progress | Low | Regression | Not Tested |  | Closed
| PreProd |  | Critical |  | N/A
| Production |  |  |  | In Progress
Tested with Showstopper

## Cases - Feature Group Chat
Test Case ID | Feature | Precondition | Positive/Negative | Scenario Name | Test Case Objective | Test Step | Expected Behaviour | Actual Behaviour | Result | Automated | Bug-ID
GroupChat01 | Send Message | User open the Group Chat | Positive | User send Message is String Group Chat | User able to send Message is String Group Chat | -Signin Google -Click Group Soal A -Click Group Chat -Put the Message is Integer -Click Icon yellow Chat Button | Success Send Message Group Message is display latest | Success Send Message Group Message is display latest | Passed | Yes
GroupChat02 |  |  | Positive | User send Message is Numeric Group Chat | User able to send Message is Numeric Group Chat | -Signin Google -Click Group Soal A -Click Group Chat -Put the Message is Numeric -Click Icon yellow Chat Button | Success Send Message Group Message is display latest | Success Send Message Group Message is display latest | Passed | Yes
GroupChat03 |  |  | Positive | User send Message is Numeric Group Chat | User able to send Message is Numeric Group Chat | -Signin Google -Click Group Soal A -Click Group Chat -Put the Message is Numeric -Click Icon yellow Chat Button | Success Send Message Group Message is display latest | Success Send Message Group Message is display latest | Passed | Yes
GroupChat04 |  |  | Positive | User send Message is GSM 7 Character Group Chat | User able to send Message is GSM 7 Character Group Chat | -Signin Google -Click Group Soal A -Click Group Chat -Put the Message is GSM 7 Chars -Click Icon yellow Chat Button | Success Send Message Group Message is display latest | Success Send Message Group Message is display latest | Passed | Yes
GroupChat05 |  |  | Positive | User send Message is UTF 8 Character Group Chat | User able to send Message is UTF 8 Character Group Chat | -Signin Google -Click Group Soal A -Click Group Chat -Put the message is UTF 8 -Click Icon yellow Chat Button | Success Send Message Group Message is display latest | Success Send Message Group Message is display latest | Passed | No
GroupChat06 |  |  | Positive | User send Message is Unicode Character Group Chat | User send Message is GSM 7 Character Group Chat | -Signin Google -Click Group Soal A -Click Group Chat -Put the Message is Unicode -Click Icon yellow Chat Button | Success Send Message Group Message is display latest | Success Send Message Group Message is display latest | Passed | Yes
GroupChat07 |  |  | Positive | User send File Screenshots Group Chat | User able to send File Group chat | -Signin Google -Click Group Soal A -Click Group Chat -Click Icon attach file -Choose File | Success Send Message Group File is display latest | Success Send Message Group File is display latest | Passed | Yes
GroupChat08 |  |  | Negative | User send File CSV Screenshots Group Chat | User not able to send File CSV Screenshots Group Chat | -Signin Google -Click Group Soal A -Click Group Chat -Click Icon attach file -Choose File CSV | Format File Cannot be allowed | Format File Cannot be allowed | Passed | No
GroupChat09 |  |  | Negative | User send File APK Group Chat | User not able to send File APK Group Chat | -Signin Google -Click Group Soal A -Click Group Chat -Click Icon attach file -Choose File APK | Format File Cannot be allowed | Format File Cannot be allowed | Passed | No
GroupChat10 |  |  | Positive | User send File XLS Group Chat | User able to send File XLS Screenshots Group Chat | -Signin Google -Click Group Soal A -Click Group Chat -Click Icon attach file -Choose File XLS | Success Send Message Group File is display latest | Success Send Message Group File is display latest | Passed | Yes
GroupChat11 |  |  | Positive | User send File Doc Screenshots Group Chat | User able to send File Doc Screenshots Group Chat | -Signin Google -Click Group Soal A -Click Group Chat -Click Icon attach file -Choose File Doc | Success Send Message Group File is display latest | Success Send Message Group File is display latest | Passed | Yes
GroupChat12 |  |  | Positive | User send File PDF Screenshots Group Chat | User send File PDF Screenshots Group Chat | -Signin Google -Click Group Soal A -Click Group Chat -Click Icon attach file -Choose File Doc | Success Send Message Group File is display latest | Success Send Message Group File is display latest | Passed | No
GroupChat13 |  |  | Positive | User send URL Group Chat | User able to send URL link Group Chat | -Signin Google -Click Group Soal A -Click Group Chat -Click Icon attach file -Choose File | Success Send Message Group URL display latest | Success Send Message Group URL display latest | Passed | Yes
GroupChat14 |  |  | Positive | User send messages 5000 char Group Chat | User able to send messages 5000 char Group Chat | -Signin Google -Click Group Soal A -Click Group Chat -Put message 5000 Chars -Choose File Videos | Success Send Message Group Messages is display latest | Success Send Message Group Messages is display latest | Passed | Yes
GroupChat15 |  |  | Positive | User attach the videos Group Chat | User able to attached videos the videos Group Chat | -Signin Google -Click Group Soal A -Click Group Chat -Click Icon Attach -Choose Video File | Success Send Message Group Videos is display latest | Success Send Message Group Videos display latest Blank Video after Downloaded | Failed | Yes | Bug001
GroupChat16 |  |  | Positive | User attach the videos Maximum File Size Group Chat | User not able attach the videos Maximum File Size Group Chat | -Signin Google -Click Group Soal A -Click Group Chat -Click Icon Attach -Choose Video File | User not able attach the videos Maximum File Size Group Chat | User not able attach the videos Maximum File Size Group Chat | Passed | No
GroupChat17 |  |  | Negative | User send messages empty Group Chat | Send Message cannot be empty | -Signin Google -Click Group Soal A -Click Group Chat -Click Icon yellow Chat Button | System does not respon when user send message is empty | System does not respon when user send message is empty | Passed | Yes
GroupChat18 | Delete Chat |  | Positive | User delete the chat | User able to deleted the chat | -Signin Google -Click Group Soal A -Click Group Chat -Select Chat will be deleted -Click Delete Message | Delete Group Chat Mesaage success | Delete Group Chat Mesaage success | Passed | Yes
GroupChat19 | Edit Profile |  | Positive | User change Photo Profile from Group Chat | User able change Photo Profile from Group Chat | -Signin Google -Click Group Soal A -Click Group Chat -Click Photo Profile -Change Photo Profile | Change Photo Profile is success | Change Photo Profile is success | Passed | No
GroupChat20 |  |  | Positive | User change Name Profile | User able to changed Photo Profile from Group Chat | -Signin Google -Click Group Soal A -Click Group Chat -Click Photo Profile -Set name Profile -Click Save | Update Name Profile is success | Update Name Profile is success | Passed | No
[9 empty] | Total Scenario | 20
[9 empty] | Total Scenario Passed | 19
[9 empty] | Total Scenario Failed | 1
[9 empty] | Total Scenario Automated | 13
[9 empty] | Total Scenario Running Manual | 7
[9 empty] | Total Scenario Positive | 17
[9 empty] | Total Scenario Negative | 3

## Cases - Feature Blast
Test Case ID | Feature | Precondition | Positive/Negative | Scenario Name | Test Case Objective | Test Step | Expected Behaviour | Actual Behaviour | Result | Automated | Bug-ID
Blast01 |  | User open the Group Chat | Positive | User publish blast | User able to publish blast | -Signin Google -Click Group Soal A -Choose Blast -Put the title -Put the story -set the Due Date -Click Publish | Create Post successfull | Create Post successfull | Passed | Yes
Blast02 |  |  | Positive | User publish blast with title emoticon | User able publish blast with title emoticon | -Signin Google -Click Group Soal A -Choose Blast -Put the title -Put the story -set the Due Date -Click Publish | Create Post successfull | Create Post successfull | Passed | Yes
Blast03 |  |  | Negative | User publish blast but Due date less than today | User not able publish blast but Due date less than today | -Signin Google -Click Group Soal A -Choose Blast -Put the title -Put the story -set the Due Date less than today -Click Publish | User not able publish blast but Due date less than today | Create Post successfull | Failed | No
Blast04 |  |  | Negative | User publish blast but Title is space | User not able publish blast but Title is space | -Signin Google -Click Group Soal A -Choose Blast -Put the title space -Click Publish | User not able publish blast but Title is space | Create Post successfull | Failed | No
Blast05 |  |  | Positive | User comment blast when blast is complete | User able to comment blast when blast is complete | -Signin Google -Click Group Soal A -Choose Blast -Select Blast with status complete -Put the comment -Click Save | User able to comment blast when blast is complete | Something When Wrong | Failed | No
Blast06 |  |  | Negative | User publish blast but all mandatory empty | All mandatory field cannot be empty | -Signin Google -Click Group Soal A -Choose Blast -Click Publish | Field Parameter not complete | Field Parameter not complete | Passed | Yes
Blast07 |  |  | Positive | User publish with set Notified | User able to publish with set Notified | -Signin Google -Click Group Soal A -Choose Blast -Put the title -Put the story -set the Due Date - Set notified -Click Publish | Create Post successfull | Create Post successfull | Passed | Yes
Blast08 | Set Format Message |  | Positive | User Blast message with format Bold | User able to Blast message with format Bold | -Signin Google -Click Group Soal A -Choose Blast -Put the title -Set Message with format Bold -Click Publish | Message can be set based on specified criteria Create Post successfull | Message can be set based on specified criteria Create Post successfull | Passed | No
Blast09 |  |  | Positive | User Blast message with format Italic | User able to Blast message with format Italic | -Signin Google -Click Group Soal A -Choose Blast -Put the title -Set Message with format Italic -Click Publish | Message can be set based on specified criteria Create Post successfull | Message can be set based on specified criteria Create Post successfull | Passed | No
Blast10 |  |  | Positive | User Blast message with format Strikethrough | User able to Blast message with format Strikethrough | -Signin Google -Click Group Soal A -Choose Blast -Put the title -Set Message with format Strikethrough -Click Publish | Message can be set based on specified criteria Create Post successfull | Message can be set based on specified criteria Create Post successfull | Passed | No
Blast11 |  |  | Positive | User Blast message with format Background Colour | User able to Blast message with format Background Colour | -Signin Google -Click Group Soal A -Choose Blast -Put the title -Set Message with format Background Color -Click Publish | Message can be set based on specified criteria Create Post successfull | Message can be set based on specified criteria Create Post successfull | Passed | No
Blast12 |  |  | Positive | User Blast message with format Font Size | User able to Blast message with format Font Size | -Signin Google -Click Group Soal A -Choose Blast -Put the title -Set Message with format Font Size -Click Publish | Message can be set based on specified criteria Create Post successfull | Message can be set based on specified criteria Create Post successfull | Passed | No
Blast13 |  |  | Positive | User Blast message with format More text | User able to Blast message with format More text | -Signin Google -Click Group Soal A -Choose Blast -Put the title -Set Message with format More Text -Click Publish | Message can be set based on specified criteria Create Post successfull | Message can be set based on specified criteria Create Post successfull | Passed | No
Blast14 |  |  | Positive | User Blast message with format Ordered List | User able to Blast message with format Ordered List | -Signin Google -Click Group Soal A -Choose Blast -Put the title -Set Message with format Ordered List -Click Publish | Message can be set based on specified criteria Create Post successfull | Message can be set based on specified criteria Create Post successfull | Passed | No
Blast15 |  |  | Positive | User Blast message with format unordered List | User able to Blast message with format unordered List | -Signin Google -Click Group Soal A -Choose Blast -Put the title -Set Message with format unordered List -Click Publish | Message can be set based on specified criteria Create Post successfull | Message can be set based on specified criteria Create Post successfull | Passed | No
Blast16 |  |  | Positive | User Blast message with format unordered More Paragraph | User able to Blast message with format More Paragraph | -Signin Google -Click Group Soal A -Choose Blast -Put the title -Set Message with format More paragraph -Click Publish | Message can be set based on specified criteria Create Post successfull | Message can be set based on specified criteria Create Post successfull | Passed | No
Blast17 |  |  | Positive | User Blast message with format Emoticon | User able to Blast message with format Emoticon | -Signin Google -Click Group Soal A -Choose Blast -Put the title -Set Message with format Emoticon -Click Publish | Message can be set based on specified criteria Create Post successfull | Message can be set based on specified criteria Create Post successfull | Passed | No
Blast18 |  |  | Positive | User Blast message with format Files | User able to Blast message with format Files | -Signin Google -Click Group Soal A -Choose Blast -Put the title -Set Message with format Files -Click Publish | Message can be set based on specified criteria Create Post successfull | Message can be set based on specified criteria Create Post successfull | Passed | No
Blast19 |  |  | Positive | User Blast message with format Insert Links | User able to Blast message with format Insert Links | -Signin Google -Click Group Soal A -Choose Blast -Put the title -Set Message with format Insert Links -Click Publish | Message can be set based on specified criteria Create Post successfull | Message can be set based on specified criteria Create Post successfull | Passed | No
Blast20 |  |  | Positive | User Blast message with format More Rich | User able to Blast message with format More Rich | -Signin Google -Click Group Soal A -Choose Blast -Put the title -Set Message with format Imore Rich -Click Publish | Message can be set based on specified criteria Create Post successfull | Message can be set based on specified criteria Create Post successfull | Passed | No
Blast21 | Set Complete |  | Positive | User Complete the Post | User able to Complete the Post | -Signin Google -Click Group Soal A -Choose Blast -Select Message Blast -Click on the checkbox Complete this post -Click Save | Set post complete successfull Redirect to list Blast Label completed display | Set post complete successfull Redirect to list Blast Label completed display | Passed | No
[9 empty] | Total Scenario | 21
[9 empty] | Total Scenario Passed | 18
[9 empty] | Total Scenario Failed | 3
[9 empty] | Total Scenario Automated | 4
[9 empty] | Total Scenario Running Manual | 17
[9 empty] | Total Scenario Positive | 18
[9 empty] | Total Scenario Negative | 3

## Findings
Jira ID (#) | Defect Name | Priority | Step to Reproduce | Expected Result | Actual Result | PIC | Status | Detected Date | Closed Date | Type | Blocked Test Case | Remarks
Bug001 | Loading Notifications never Stop | Normal | -Signin Google -Click Icon Notifications | All Notifications displayed correctly | Intermittent Notification not displayed correctly | Tim Development | Open | 2021-10-25
Bug002 | User Edit Due Date but less than today | Normal | -Signin Google -Click Group Soal A -Click Board -Select Card -Select Edit Due Date -Set the Date -Set the Time -Click Save Button | Due date cannot be less than today | Update Card is success | Tim Development | Open | 2021-10-25
Bug003 | User attach the videos Group Chat | High | -Signin Google -Click Group Soal A -Click Group Chat -Click Icon Attach -Choose Video File | Success Send Message Group Videos is display latest | Success Send Message Group Videos display latest Blank Video after Downloaded | Tim Development | Open | 2021-10-25
Bug004 | User publish blast but Due date less than today | High | -Signin Google -Click Group Soal A -Choose Blast -Put the title -Put the story -set the Due Date less than today -Click Publish | User not able publish blast but Due date less than today | Create Post successfull | Tim Development | Open | 2021-10-25
Bug005 | User publish blast but Title is space | Normal | -Signin Google -Click Group Soal A -Choose Blast -Put the title space -Click Publish | User not able publish blast but Title is space | Create Post successfull | Tim Development | Open | 2021-10-25
Bug006 | User comment blast when blast is complete | Normal | -Signin Google -Click Group Soal A -Choose Blast -Select Blast with status complete -Put the comment -Click Save | User able to comment blast when blast is complete | Something When Wrong | Tim Development | Open | 2021-10-25
[8 empty] | Total Findings | 6
[8 empty] | Bug Priority Immadiate | 0
[8 empty] | Bug Priority High | 2
[8 empty] | Bug Priority Normal | 4
[8 empty] | Bug Priority Low | 0